## Report Information
Property | Value
Report Name | Supply Chain Disruption Report
Description | Real-time disruption monitoring and mitigation
Generated By | Vanguard Disruption Manager
Use Case | supply-chain-disruption
Workflow ID | disruption-report
Generated At | 2025-08-03T13:05:43.554Z

## Active Disruptions
Disruption ID | Type | Severity | Location | Started | Est. Resolution | Affected Routes | Delayed Deliveries | Additional Cost
DISR-00001 | ACCIDENT | CRITICAL | Port of LA | 8/1/2025, 8:05:43 PM | 8/2/2025, 2:05:43 AM | 5 | 45 | $7,596.202
DISR-00002 | WEATHER | LOW | Mexican Border | 8/1/2025, 4:05:43 PM | 8/1/2025, 7:05:43 PM | 1 | 11 | $2,160.317
DISR-00006 | CUSTOMS | LOW | Port of LA | 8/2/2025, 11:05:43 AM | 8/3/2025, 10:05:43 AM | 2 | 26 | $2,474.142
DISR-00009 | WEATHER | MEDIUM | Port of LA | 8/1/2025, 11:05:43 AM | 8/2/2025, 10:05:43 AM | 4 | 48 | $2,926.433
DISR-00010 | WEATHER | MEDIUM | Chicago Hub | 8/2/2025, 1:05:43 PM | 8/2/2025, 11:05:43 PM | 2 | 10 | $1,493.416

## Impact Analysis
Metric | Value
Total Disruptions | 10
Active Disruptions | 5
Total Delayed Deliveries | 453
Total Additional Cost | $63,973.178
Affected Customers | 362
Average Resolution Time | 4.5 hours

## Mitigation Actions
Disruption ID | Action | Priority | Status | Responsible
DISR-00001 | Reroute affected vehicles | IMMEDIATE | In Progress | Operations Team
DISR-00001 | Notify customers of delays | IMMEDIATE | In Progress | Operations Team
DISR-00001 | Deploy backup resources | IMMEDIATE | Planned | Operations Team
DISR-00002 | Reroute affected vehicles | MEDIUM | Planned | Operations Team
DISR-00002 | Notify customers of delays | MEDIUM | Planned | Operations Team
DISR-00006 | Reroute affected vehicles | MEDIUM | Planned | Operations Team
DISR-00006 | Notify customers of delays | MEDIUM | Planned | Operations Team
DISR-00006 | Deploy backup resources | MEDIUM | Planned | Operations Team
DISR-00009 | Reroute affected vehicles | MEDIUM | In Progress | Operations Team
DISR-00009 | Notify customers of delays | MEDIUM | In Progress | Operations Team
DISR-00010 | Reroute affected vehicles | MEDIUM | Planned | Operations Team
DISR-00010 | Notify customers of delays | MEDIUM | In Progress | Operations Team

## Historical Analysis
Month | Disruptions | Avg Resolution (hrs) | Total Cost
January | 12 | 4.2 | $45,000
February | 8 | 3.8 | $32,000
March | 15 | 5.1 | $58,000
April | 10 | 3.5 | $38,000