## Report Information
Property | Value
Report Name | Supply Chain Disruption Report
Description | Real-time disruption monitoring and mitigation
Generated By | Vanguard Disruption Manager
Use Case | supply-chain-disruption
Workflow ID | disruption-report
Generated At | 2025-08-03T13:07:14.383Z

## Active Disruptions
Disruption ID | Type | Severity | Location | Started | Est. Resolution | Affected Routes | Delayed Deliveries | Additional Cost
DISR-00003 | EQUIPMENT | CRITICAL | Highway 101 | 8/2/2025, 9:07:14 PM | 8/3/2025, 1:07:14 PM | 3 | 39 | $7,703.964
DISR-00004 | CUSTOMS | HIGH | Mexican Border | 8/2/2025, 11:07:14 PM | 8/3/2025, 12:07:14 PM | 1 | 8 | $647.137
DISR-00007 | WEATHER | MEDIUM | Port of LA | 8/2/2025, 3:07:14 AM | 8/2/2025, 7:07:14 AM | 8 | 56 | $11,094.208
DISR-00008 | TRAFFIC | CRITICAL | Port of LA | 8/1/2025, 8:07:14 PM | 8/2/2025, 7:07:14 PM | 3 | 21 | $3,393.074
DISR-00010 | STRIKE | HIGH | Port of LA | 8/1/2025, 2:07:14 PM | 8/1/2025, 4:07:14 PM | 5 | 50 | $6,133.994

## Impact Analysis
Metric | Value
Total Disruptions | 10
Active Disruptions | 5
Total Delayed Deliveries | 553
Total Additional Cost | $84,559.835
Affected Customers | 442
Average Resolution Time | 4.5 hours

## Mitigation Actions
Disruption ID | Action | Priority | Status | Responsible
DISR-00003 | Reroute affected vehicles | IMMEDIATE | Planned | Operations Team
DISR-00003 | Notify customers of delays | IMMEDIATE | Planned | Operations Team
DISR-00004 | Reroute affected vehicles | HIGH | In Progress | Operations Team
DISR-00004 | Notify customers of delays | HIGH | In Progress | Operations Team
DISR-00007 | Reroute affected vehicles | MEDIUM | In Progress | Operations Team
DISR-00007 | Notify customers of delays | MEDIUM | In Progress | Operations Team
DISR-00008 | Reroute affected vehicles | IMMEDIATE | In Progress | Operations Team
DISR-00008 | Notify customers of delays | IMMEDIATE | Planned | Operations Team
DISR-00008 | Deploy backup resources | IMMEDIATE | In Progress | Operations Team
DISR-00010 | Reroute affected vehicles | HIGH | Planned | Operations Team
DISR-00010 | Notify customers of delays | HIGH | In Progress | Operations Team
DISR-00010 | Deploy backup resources | HIGH | In Progress | Operations Team

## Historical Analysis
Month | Disruptions | Avg Resolution (hrs) | Total Cost
January | 12 | 4.2 | $45,000
February | 8 | 3.8 | $32,000
March | 15 | 5.1 | $58,000
April | 10 | 3.5 | $38,000