## Report Information
Property | Value
Report Name | Supply Chain Disruption Report
Description | Real-time disruption monitoring and mitigation
Generated By | Vanguard Disruption Manager
Use Case | supply-chain-disruption
Workflow ID | disruption-report
Generated At | 2025-08-03T13:02:59.032Z

## Active Disruptions
Disruption ID | Type | Severity | Location | Started | Est. Resolution | Affected Routes | Delayed Deliveries | Additional Cost
DISR-00002 | STRIKE | HIGH | Highway 101 | 8/3/2025, 6:02:59 AM | 8/3/2025, 6:02:59 PM | 5 | 45 | $4,588.778
DISR-00003 | EQUIPMENT | HIGH | Chicago Hub | 8/1/2025, 10:02:59 AM | 8/1/2025, 3:02:59 PM | 2 | 28 | $2,952.948
DISR-00004 | ACCIDENT | LOW | Highway 101 | 8/3/2025, 2:02:59 AM | 8/3/2025, 9:02:59 PM | 10 | 60 | $10,133.062
DISR-00005 | EQUIPMENT | CRITICAL | Highway 101 | 8/1/2025, 11:02:59 AM | 8/1/2025, 5:02:59 PM | 6 | 54 | $3,313.557
DISR-00006 | EQUIPMENT | CRITICAL | Mexican Border | 8/2/2025, 12:02:59 AM | 8/2/2025, 11:02:59 AM | 2 | 22 | $2,531.794
DISR-00009 | CUSTOMS | LOW | Chicago Hub | 8/2/2025, 11:02:59 AM | 8/2/2025, 9:02:59 PM | 6 | 54 | $3,993.965
DISR-00010 | WEATHER | CRITICAL | Highway 101 | 8/2/2025, 11:02:59 AM | 8/3/2025, 11:02:59 AM | 4 | 40 | $5,505.624

## Impact Analysis
Metric | Value
Total Disruptions | 10
Active Disruptions | 7
Total Delayed Deliveries | 442
Total Additional Cost | $46,334.574
Affected Customers | 353
Average Resolution Time | 4.5 hours

## Mitigation Actions
Disruption ID | Action | Priority | Status | Responsible
DISR-00002 | Reroute affected vehicles | HIGH | In Progress | Operations Team
DISR-00002 | Notify customers of delays | HIGH | Planned | Operations Team
DISR-00003 | Reroute affected vehicles | HIGH | Planned | Operations Team
DISR-00003 | Notify customers of delays | HIGH | Planned | Operations Team
DISR-00004 | Reroute affected vehicles | MEDIUM | Planned | Operations Team
DISR-00004 | Notify customers of delays | MEDIUM | Planned | Operations Team
DISR-00005 | Reroute affected vehicles | IMMEDIATE | In Progress | Operations Team
DISR-00005 | Notify customers of delays | IMMEDIATE | Planned | Operations Team
DISR-00006 | Reroute affected vehicles | IMMEDIATE | Planned | Operations Team
DISR-00006 | Notify customers of delays | IMMEDIATE | In Progress | Operations Team
DISR-00009 | Reroute affected vehicles | MEDIUM | Planned | Operations Team
DISR-00009 | Notify customers of delays | MEDIUM | Planned | Operations Team
DISR-00009 | Deploy backup resources | MEDIUM | Planned | Operations Team
DISR-00010 | Reroute affected vehicles | IMMEDIATE | Planned | Operations Team
DISR-00010 | Notify customers of delays | IMMEDIATE | Planned | Operations Team

## Historical Analysis
Month | Disruptions | Avg Resolution (hrs) | Total Cost
January | 12 | 4.2 | $45,000
February | 8 | 3.8 | $32,000
March | 15 | 5.1 | $58,000
April | 10 | 3.5 | $38,000