## Report Information
Property | Value
Report Name | Supply Chain Disruption Report
Description | Real-time disruption monitoring and mitigation
Generated By | Vanguard Disruption Manager
Use Case | supply-chain-disruption
Workflow ID | disruption-report
Generated At | 2025-08-03T13:05:30.649Z

## Active Disruptions
Disruption ID | Type | Severity | Location | Started | Est. Resolution | Affected Routes | Delayed Deliveries | Additional Cost
DISR-00002 | ACCIDENT | HIGH | Port of LA | 8/1/2025, 11:05:30 AM | 8/1/2025, 8:05:30 PM | 2 | 24 | $3,516.935
DISR-00003 | CUSTOMS | CRITICAL | Chicago Hub | 8/1/2025, 9:05:30 AM | 8/2/2025, 8:05:30 AM | 7 | 98 | $8,485.343
DISR-00005 | WEATHER | MEDIUM | JFK Airport | 8/1/2025, 9:05:30 AM | 8/2/2025, 8:05:30 AM | 3 | 21 | $2,811.514
DISR-00006 | TRAFFIC | HIGH | JFK Airport | 8/2/2025, 3:05:30 AM | 8/2/2025, 7:05:30 AM | 2 | 20 | $3,086.873
DISR-00008 | TRAFFIC | CRITICAL | Chicago Hub | 8/1/2025, 3:05:30 PM | 8/2/2025, 3:05:30 PM | 3 | 15 | $2,746.548
DISR-00009 | CUSTOMS | MEDIUM | Chicago Hub | 8/2/2025, 6:05:30 AM | 8/2/2025, 12:05:30 PM | 2 | 16 | $1,401.975
DISR-00010 | TRAFFIC | HIGH | Port of LA | 8/2/2025, 7:05:30 PM | 8/3/2025, 1:05:30 PM | 3 | 39 | $5,208.728

## Impact Analysis
Metric | Value
Total Disruptions | 10
Active Disruptions | 7
Total Delayed Deliveries | 412
Total Additional Cost | $45,104.838
Affected Customers | 329
Average Resolution Time | 4.5 hours

## Mitigation Actions
Disruption ID | Action | Priority | Status | Responsible
DISR-00002 | Reroute affected vehicles | HIGH | In Progress | Operations Team
DISR-00002 | Notify customers of delays | HIGH | Planned | Operations Team
DISR-00003 | Reroute affected vehicles | IMMEDIATE | In Progress | Operations Team
DISR-00003 | Notify customers of delays | IMMEDIATE | In Progress | Operations Team
DISR-00003 | Deploy backup resources | IMMEDIATE | Planned | Operations Team
DISR-00005 | Reroute affected vehicles | MEDIUM | Planned | Operations Team
DISR-00005 | Notify customers of delays | MEDIUM | In Progress | Operations Team
DISR-00006 | Reroute affected vehicles | HIGH | Planned | Operations Team
DISR-00006 | Notify customers of delays | HIGH | In Progress | Operations Team
DISR-00006 | Deploy backup resources | HIGH | In Progress | Operations Team
DISR-00008 | Reroute affected vehicles | IMMEDIATE | Planned | Operations Team
DISR-00008 | Notify customers of delays | IMMEDIATE | In Progress | Operations Team
DISR-00009 | Reroute affected vehicles | MEDIUM | In Progress | Operations Team
DISR-00009 | Notify customers of delays | MEDIUM | In Progress | Operations Team
DISR-00009 | Deploy backup resources | MEDIUM | In Progress | Operations Team
DISR-00010 | Reroute affected vehicles | HIGH | Planned | Operations Team
DISR-00010 | Notify customers of delays | HIGH | In Progress | Operations Team

## Historical Analysis
Month | Disruptions | Avg Resolution (hrs) | Total Cost
January | 12 | 4.2 | $45,000
February | 8 | 3.8 | $32,000
March | 15 | 5.1 | $58,000
April | 10 | 3.5 | $38,000