## Report Information
Property | Value
Report Name | Supply Chain Disruption Report
Description | Real-time disruption monitoring and mitigation
Generated By | Vanguard Disruption Manager
Use Case | supply-chain-disruption
Workflow ID | disruption-report
Generated At | 2025-08-03T13:01:08.866Z

## Active Disruptions
Disruption ID | Type | Severity | Location | Started | Est. Resolution | Affected Routes | Delayed Deliveries | Additional Cost
DISR-00001 | WEATHER | HIGH | Port of LA | 8/2/2025, 8:01:08 PM | 8/3/2025, 12:01:08 AM | 9 | 108 | $19,546.8
DISR-00005 | ACCIDENT | HIGH | JFK Airport | 8/2/2025, 6:01:08 PM | 8/3/2025, 12:01:08 PM | 4 | 48 | $7,726.022
DISR-00007 | CUSTOMS | HIGH | Port of LA | 8/1/2025, 9:01:08 AM | 8/1/2025, 11:01:08 PM | 9 | 126 | $8,292.203

## Impact Analysis
Metric | Value
Total Disruptions | 10
Active Disruptions | 3
Total Delayed Deliveries | 693
Total Additional Cost | $84,198.568
Affected Customers | 554
Average Resolution Time | 4.5 hours

## Mitigation Actions
Disruption ID | Action | Priority | Status | Responsible
DISR-00001 | Reroute affected vehicles | HIGH | Planned | Operations Team
DISR-00001 | Notify customers of delays | HIGH | In Progress | Operations Team
DISR-00001 | Deploy backup resources | HIGH | In Progress | Operations Team
DISR-00005 | Reroute affected vehicles | HIGH | In Progress | Operations Team
DISR-00005 | Notify customers of delays | HIGH | In Progress | Operations Team
DISR-00005 | Deploy backup resources | HIGH | In Progress | Operations Team
DISR-00007 | Reroute affected vehicles | HIGH | In Progress | Operations Team
DISR-00007 | Notify customers of delays | HIGH | Planned | Operations Team

## Historical Analysis
Month | Disruptions | Avg Resolution (hrs) | Total Cost
January | 12 | 4.2 | $45,000
February | 8 | 3.8 | $32,000
March | 15 | 5.1 | $58,000
April | 10 | 3.5 | $38,000