## Report Information
Property | Value
Report Name | Supply Chain Disruption Report
Description | Real-time disruption monitoring and mitigation
Generated By | Vanguard Disruption Manager
Use Case | supply-chain-disruption
Workflow ID | disruption-report
Generated At | 2025-08-03T13:02:03.277Z

## Active Disruptions
Disruption ID | Type | Severity | Location | Started | Est. Resolution | Affected Routes | Delayed Deliveries | Additional Cost
DISR-00002 | WEATHER | HIGH | Highway 101 | 8/1/2025, 9:02:03 PM | 8/2/2025, 4:02:03 AM | 6 | 78 | $11,276.338
DISR-00005 | WEATHER | LOW | Port of LA | 8/2/2025, 10:02:03 PM | 8/3/2025, 6:02:03 PM | 2 | 12 | $857.897

## Impact Analysis
Metric | Value
Total Disruptions | 10
Active Disruptions | 2
Total Delayed Deliveries | 536
Total Additional Cost | $69,243.796
Affected Customers | 428
Average Resolution Time | 4.5 hours

## Mitigation Actions
Disruption ID | Action | Priority | Status | Responsible
DISR-00002 | Reroute affected vehicles | HIGH | In Progress | Operations Team
DISR-00002 | Notify customers of delays | HIGH | In Progress | Operations Team
DISR-00002 | Deploy backup resources | HIGH | Planned | Operations Team
DISR-00005 | Reroute affected vehicles | MEDIUM | Planned | Operations Team
DISR-00005 | Notify customers of delays | MEDIUM | In Progress | Operations Team
DISR-00005 | Deploy backup resources | MEDIUM | In Progress | Operations Team

## Historical Analysis
Month | Disruptions | Avg Resolution (hrs) | Total Cost
January | 12 | 4.2 | $45,000
February | 8 | 3.8 | $32,000
March | 15 | 5.1 | $58,000
April | 10 | 3.5 | $38,000