## Report Information
Property | Value
Report Name | Supply Chain Disruption Report
Description | Real-time disruption monitoring and mitigation
Generated By | Vanguard Disruption Manager
Use Case | supply-chain-disruption
Workflow ID | disruption-report
Generated At | 2025-08-03T13:06:54.285Z

## Active Disruptions
Disruption ID | Type | Severity | Location | Started | Est. Resolution | Affected Routes | Delayed Deliveries | Additional Cost
DISR-00004 | EQUIPMENT | LOW | Highway 101 | 8/2/2025, 5:06:54 PM | 8/2/2025, 9:06:54 PM | 5 | 65 | $8,919.474
DISR-00007 | EQUIPMENT | MEDIUM | Port of LA | 8/1/2025, 1:06:54 PM | 8/2/2025, 4:06:54 AM | 10 | 100 | $6,490.223
DISR-00008 | TRAFFIC | HIGH | Mexican Border | 8/1/2025, 11:06:54 PM | 8/2/2025, 8:06:54 PM | 1 | 13 | $844.504
DISR-00009 | WEATHER | MEDIUM | JFK Airport | 8/2/2025, 9:06:54 PM | 8/3/2025, 12:06:54 PM | 6 | 54 | $3,483.716
DISR-00010 | TRAFFIC | LOW | Chicago Hub | 8/1/2025, 4:06:54 PM | 8/2/2025, 5:06:54 PM | 8 | 112 | $14,520.404

## Impact Analysis
Metric | Value
Total Disruptions | 10
Active Disruptions | 5
Total Delayed Deliveries | 701
Total Additional Cost | $75,827.458
Affected Customers | 560
Average Resolution Time | 4.5 hours

## Mitigation Actions
Disruption ID | Action | Priority | Status | Responsible
DISR-00004 | Reroute affected vehicles | MEDIUM | Planned | Operations Team
DISR-00004 | Notify customers of delays | MEDIUM | In Progress | Operations Team
DISR-00004 | Deploy backup resources | MEDIUM | In Progress | Operations Team
DISR-00007 | Reroute affected vehicles | MEDIUM | Planned | Operations Team
DISR-00007 | Notify customers of delays | MEDIUM | Planned | Operations Team
DISR-00007 | Deploy backup resources | MEDIUM | In Progress | Operations Team
DISR-00008 | Reroute affected vehicles | HIGH | Planned | Operations Team
DISR-00008 | Notify customers of delays | HIGH | Planned | Operations Team
DISR-00008 | Deploy backup resources | HIGH | Planned | Operations Team
DISR-00009 | Reroute affected vehicles | MEDIUM | Planned | Operations Team
DISR-00009 | Notify customers of delays | MEDIUM | In Progress | Operations Team
DISR-00009 | Deploy backup resources | MEDIUM | In Progress | Operations Team
DISR-00010 | Reroute affected vehicles | MEDIUM | In Progress | Operations Team
DISR-00010 | Notify customers of delays | MEDIUM | Planned | Operations Team

## Historical Analysis
Month | Disruptions | Avg Resolution (hrs) | Total Cost
January | 12 | 4.2 | $45,000
February | 8 | 3.8 | $32,000
March | 15 | 5.1 | $58,000
April | 10 | 3.5 | $38,000