## Report Information
Property | Value
Report Name | Supply Chain Disruption Report
Description | Real-time disruption monitoring and mitigation
Generated By | Vanguard Disruption Manager
Use Case | supply-chain-disruption
Workflow ID | disruption-report
Generated At | 2025-08-03T13:01:29.326Z

## Active Disruptions
Disruption ID | Type | Severity | Location | Started | Est. Resolution | Affected Routes | Delayed Deliveries | Additional Cost
DISR-00002 | TRAFFIC | CRITICAL | Mexican Border | 8/2/2025, 7:01:29 PM | 8/3/2025, 7:01:29 PM | 9 | 117 | $12,460.766
DISR-00003 | TRAFFIC | LOW | Highway 101 | 8/3/2025, 4:01:29 AM | 8/4/2025, 2:01:29 AM | 8 | 40 | $2,784.161
DISR-00007 | TRAFFIC | MEDIUM | JFK Airport | 8/2/2025, 9:01:29 PM | 8/3/2025, 12:01:29 AM | 8 | 96 | $12,647.398
DISR-00009 | CUSTOMS | HIGH | Highway 101 | 8/3/2025, 7:01:29 AM | 8/3/2025, 3:01:29 PM | 5 | 50 | $2,954.48

## Impact Analysis
Metric | Value
Total Disruptions | 10
Active Disruptions | 4
Total Delayed Deliveries | 702
Total Additional Cost | $92,358.04
Affected Customers | 561
Average Resolution Time | 4.5 hours

## Mitigation Actions
Disruption ID | Action | Priority | Status | Responsible
DISR-00002 | Reroute affected vehicles | IMMEDIATE | Planned | Operations Team
DISR-00002 | Notify customers of delays | IMMEDIATE | In Progress | Operations Team
DISR-00002 | Deploy backup resources | IMMEDIATE | In Progress | Operations Team
DISR-00003 | Reroute affected vehicles | MEDIUM | Planned | Operations Team
DISR-00003 | Notify customers of delays | MEDIUM | In Progress | Operations Team
DISR-00003 | Deploy backup resources | MEDIUM | In Progress | Operations Team
DISR-00007 | Reroute affected vehicles | MEDIUM | Planned | Operations Team
DISR-00007 | Notify customers of delays | MEDIUM | Planned | Operations Team
DISR-00007 | Deploy backup resources | MEDIUM | Planned | Operations Team
DISR-00009 | Reroute affected vehicles | HIGH | Planned | Operations Team
DISR-00009 | Notify customers of delays | HIGH | Planned | Operations Team

## Historical Analysis
Month | Disruptions | Avg Resolution (hrs) | Total Cost
January | 12 | 4.2 | $45,000
February | 8 | 3.8 | $32,000
March | 15 | 5.1 | $58,000
April | 10 | 3.5 | $38,000