## Report Information
Property | Value
Report Name | Supply Chain Disruption Report
Description | Real-time disruption monitoring and mitigation
Generated By | Vanguard Disruption Manager
Use Case | supply-chain-disruption
Workflow ID | disruption-report
Generated At | 2025-08-03T13:06:53.602Z

## Active Disruptions
Disruption ID | Type | Severity | Location | Started | Est. Resolution | Affected Routes | Delayed Deliveries | Additional Cost
DISR-00001 | WEATHER | HIGH | Highway 101 | 8/2/2025, 3:06:53 AM | 8/2/2025, 11:06:53 AM | 5 | 70 | $6,605.007
DISR-00003 | WEATHER | LOW | Mexican Border | 8/2/2025, 3:06:53 AM | 8/2/2025, 5:06:53 AM | 2 | 12 | $1,743.223
DISR-00005 | ACCIDENT | LOW | JFK Airport | 8/2/2025, 5:06:53 PM | 8/3/2025, 12:06:53 AM | 3 | 24 | $1,976.96
DISR-00008 | STRIKE | CRITICAL | Chicago Hub | 8/2/2025, 2:06:53 PM | 8/3/2025, 9:06:53 AM | 4 | 32 | $3,518.097

## Impact Analysis
Metric | Value
Total Disruptions | 10
Active Disruptions | 4
Total Delayed Deliveries | 450
Total Additional Cost | $50,084.163
Affected Customers | 360
Average Resolution Time | 4.5 hours

## Mitigation Actions
Disruption ID | Action | Priority | Status | Responsible
DISR-00001 | Reroute affected vehicles | HIGH | In Progress | Operations Team
DISR-00001 | Notify customers of delays | HIGH | Planned | Operations Team
DISR-00003 | Reroute affected vehicles | MEDIUM | In Progress | Operations Team
DISR-00003 | Notify customers of delays | MEDIUM | Planned | Operations Team
DISR-00003 | Deploy backup resources | MEDIUM | Planned | Operations Team
DISR-00005 | Reroute affected vehicles | MEDIUM | Planned | Operations Team
DISR-00005 | Notify customers of delays | MEDIUM | Planned | Operations Team
DISR-00005 | Deploy backup resources | MEDIUM | Planned | Operations Team
DISR-00008 | Reroute affected vehicles | IMMEDIATE | In Progress | Operations Team
DISR-00008 | Notify customers of delays | IMMEDIATE | In Progress | Operations Team

## Historical Analysis
Month | Disruptions | Avg Resolution (hrs) | Total Cost
January | 12 | 4.2 | $45,000
February | 8 | 3.8 | $32,000
March | 15 | 5.1 | $58,000
April | 10 | 3.5 | $38,000