## Report Information
Property | Value
Report Name | Supply Chain Disruption Report
Description | Real-time disruption monitoring and mitigation
Generated By | Vanguard Disruption Manager
Use Case | supply-chain-disruption
Workflow ID | disruption-report
Generated At | 2025-08-03T13:04:30.351Z

## Active Disruptions
Disruption ID | Type | Severity | Location | Started | Est. Resolution | Affected Routes | Delayed Deliveries | Additional Cost
DISR-00003 | STRIKE | CRITICAL | Chicago Hub | 8/2/2025, 11:04:30 PM | 8/3/2025, 11:04:30 PM | 8 | 72 | $6,525.554
DISR-00004 | TRAFFIC | HIGH | JFK Airport | 8/1/2025, 10:04:30 PM | 8/2/2025, 10:04:30 AM | 1 | 6 | $446.812
DISR-00007 | TRAFFIC | LOW | Chicago Hub | 8/2/2025, 12:04:30 PM | 8/3/2025, 2:04:30 AM | 4 | 48 | $6,342.447
DISR-00008 | CUSTOMS | LOW | Port of LA | 8/1/2025, 2:04:30 PM | 8/2/2025, 1:04:30 PM | 1 | 14 | $1,404.511

## Impact Analysis
Metric | Value
Total Disruptions | 10
Active Disruptions | 4
Total Delayed Deliveries | 424
Total Additional Cost | $46,334.217
Affected Customers | 339
Average Resolution Time | 4.5 hours

## Mitigation Actions
Disruption ID | Action | Priority | Status | Responsible
DISR-00003 | Reroute affected vehicles | IMMEDIATE | Planned | Operations Team
DISR-00003 | Notify customers of delays | IMMEDIATE | In Progress | Operations Team
DISR-00004 | Reroute affected vehicles | HIGH | In Progress | Operations Team
DISR-00004 | Notify customers of delays | HIGH | Planned | Operations Team
DISR-00004 | Deploy backup resources | HIGH | In Progress | Operations Team
DISR-00007 | Reroute affected vehicles | MEDIUM | Planned | Operations Team
DISR-00007 | Notify customers of delays | MEDIUM | In Progress | Operations Team
DISR-00008 | Reroute affected vehicles | MEDIUM | In Progress | Operations Team
DISR-00008 | Notify customers of delays | MEDIUM | Planned | Operations Team
DISR-00008 | Deploy backup resources | MEDIUM | In Progress | Operations Team

## Historical Analysis
Month | Disruptions | Avg Resolution (hrs) | Total Cost
January | 12 | 4.2 | $45,000
February | 8 | 3.8 | $32,000
March | 15 | 5.1 | $58,000
April | 10 | 3.5 | $38,000