## Report Information
Property | Value
Report Name | Supply Chain Disruption Report
Description | Real-time disruption monitoring and mitigation
Generated By | Vanguard Disruption Manager
Use Case | supply-chain-disruption
Workflow ID | disruption-report
Generated At | 2025-08-03T13:07:26.141Z

## Active Disruptions
Disruption ID | Type | Severity | Location | Started | Est. Resolution | Affected Routes | Delayed Deliveries | Additional Cost
DISR-00003 | CUSTOMS | LOW | Mexican Border | 8/2/2025, 4:07:26 AM | 8/2/2025, 9:07:26 AM | 4 | 44 | $4,891.895
DISR-00004 | CUSTOMS | MEDIUM | Highway 101 | 8/1/2025, 12:07:26 PM | 8/1/2025, 11:07:26 PM | 10 | 90 | $9,528.726
DISR-00006 | TRAFFIC | HIGH | JFK Airport | 8/1/2025, 7:07:26 PM | 8/2/2025, 5:07:26 PM | 4 | 44 | $8,059.815
DISR-00007 | WEATHER | CRITICAL | Chicago Hub | 8/2/2025, 11:07:26 AM | 8/2/2025, 3:07:26 PM | 8 | 56 | $10,138.216
DISR-00009 | ACCIDENT | CRITICAL | JFK Airport | 8/1/2025, 11:07:26 AM | 8/1/2025, 10:07:26 PM | 7 | 70 | $6,975.092
DISR-00010 | EQUIPMENT | MEDIUM | Port of LA | 8/2/2025, 1:07:26 PM | 8/2/2025, 7:07:26 PM | 1 | 5 | $744.682

## Impact Analysis
Metric | Value
Total Disruptions | 10
Active Disruptions | 6
Total Delayed Deliveries | 495
Total Additional Cost | $56,596.104
Affected Customers | 396
Average Resolution Time | 4.5 hours

## Mitigation Actions
Disruption ID | Action | Priority | Status | Responsible
DISR-00003 | Reroute affected vehicles | MEDIUM | Planned | Operations Team
DISR-00003 | Notify customers of delays | MEDIUM | In Progress | Operations Team
DISR-00003 | Deploy backup resources | MEDIUM | Planned | Operations Team
DISR-00004 | Reroute affected vehicles | MEDIUM | Planned | Operations Team
DISR-00004 | Notify customers of delays | MEDIUM | In Progress | Operations Team
DISR-00004 | Deploy backup resources | MEDIUM | Planned | Operations Team
DISR-00006 | Reroute affected vehicles | HIGH | Planned | Operations Team
DISR-00006 | Notify customers of delays | HIGH | Planned | Operations Team
DISR-00007 | Reroute affected vehicles | IMMEDIATE | Planned | Operations Team
DISR-00007 | Notify customers of delays | IMMEDIATE | In Progress | Operations Team
DISR-00007 | Deploy backup resources | IMMEDIATE | In Progress | Operations Team
DISR-00009 | Reroute affected vehicles | IMMEDIATE | In Progress | Operations Team
DISR-00009 | Notify customers of delays | IMMEDIATE | Planned | Operations Team
DISR-00009 | Deploy backup resources | IMMEDIATE | In Progress | Operations Team
DISR-00010 | Reroute affected vehicles | MEDIUM | Planned | Operations Team
DISR-00010 | Notify customers of delays | MEDIUM | In Progress | Operations Team

## Historical Analysis
Month | Disruptions | Avg Resolution (hrs) | Total Cost
January | 12 | 4.2 | $45,000
February | 8 | 3.8 | $32,000
March | 15 | 5.1 | $58,000
April | 10 | 3.5 | $38,000