## Report Information
Property | Value
Report Name | Supply Chain Disruption Report
Description | Real-time disruption monitoring and mitigation
Generated By | Vanguard Disruption Manager
Use Case | supply-chain-disruption
Workflow ID | disruption-report
Generated At | 2025-08-03T13:03:29.220Z

## Active Disruptions
Disruption ID | Type | Severity | Location | Started | Est. Resolution | Affected Routes | Delayed Deliveries | Additional Cost
DISR-00002 | WEATHER | MEDIUM | Mexican Border | 8/2/2025, 6:03:29 AM | 8/2/2025, 9:03:29 PM | 6 | 84 | $12,479.865
DISR-00003 | ACCIDENT | LOW | Chicago Hub | 8/1/2025, 8:03:29 PM | 8/2/2025, 5:03:29 AM | 2 | 10 | $819.273
DISR-00005 | STRIKE | MEDIUM | Port of LA | 8/1/2025, 5:03:29 PM | 8/2/2025, 7:03:29 AM | 3 | 36 | $5,317.081
DISR-00010 | ACCIDENT | MEDIUM | JFK Airport | 8/2/2025, 4:03:29 PM | 8/3/2025, 5:03:29 PM | 7 | 63 | $6,748.105

## Impact Analysis
Metric | Value
Total Disruptions | 10
Active Disruptions | 4
Total Delayed Deliveries | 550
Total Additional Cost | $68,219.677
Affected Customers | 440
Average Resolution Time | 4.5 hours

## Mitigation Actions
Disruption ID | Action | Priority | Status | Responsible
DISR-00002 | Reroute affected vehicles | MEDIUM | In Progress | Operations Team
DISR-00002 | Notify customers of delays | MEDIUM | Planned | Operations Team
DISR-00002 | Deploy backup resources | MEDIUM | In Progress | Operations Team
DISR-00003 | Reroute affected vehicles | MEDIUM | Planned | Operations Team
DISR-00003 | Notify customers of delays | MEDIUM | In Progress | Operations Team
DISR-00003 | Deploy backup resources | MEDIUM | Planned | Operations Team
DISR-00005 | Reroute affected vehicles | MEDIUM | Planned | Operations Team
DISR-00005 | Notify customers of delays | MEDIUM | In Progress | Operations Team
DISR-00005 | Deploy backup resources | MEDIUM | In Progress | Operations Team
DISR-00010 | Reroute affected vehicles | MEDIUM | In Progress | Operations Team
DISR-00010 | Notify customers of delays | MEDIUM | Planned | Operations Team
DISR-00010 | Deploy backup resources | MEDIUM | In Progress | Operations Team

## Historical Analysis
Month | Disruptions | Avg Resolution (hrs) | Total Cost
January | 12 | 4.2 | $45,000
February | 8 | 3.8 | $32,000
March | 15 | 5.1 | $58,000
April | 10 | 3.5 | $38,000