## Report Information
Property | Value
Report Name | Supply Chain Disruption Report
Description | Real-time disruption monitoring and mitigation
Generated By | Vanguard Disruption Manager
Use Case | supply-chain-disruption
Workflow ID | disruption-report
Generated At | 2025-08-03T13:04:53.712Z

## Active Disruptions
Disruption ID | Type | Severity | Location | Started | Est. Resolution | Affected Routes | Delayed Deliveries | Additional Cost
DISR-00001 | CUSTOMS | LOW | Mexican Border | 8/2/2025, 12:04:53 AM | 8/2/2025, 4:04:53 PM | 5 | 50 | $2,744.369
DISR-00004 | ACCIDENT | CRITICAL | Mexican Border | 8/1/2025, 12:04:53 PM | 8/1/2025, 3:04:53 PM | 7 | 84 | $12,977.422
DISR-00005 | TRAFFIC | CRITICAL | Chicago Hub | 8/1/2025, 10:04:53 PM | 8/2/2025, 8:04:53 AM | 8 | 80 | $7,409.627
DISR-00006 | EQUIPMENT | CRITICAL | JFK Airport | 8/2/2025, 10:04:53 PM | 8/3/2025, 11:04:53 AM | 10 | 120 | $8,193.457
DISR-00009 | TRAFFIC | HIGH | Chicago Hub | 8/2/2025, 12:04:53 AM | 8/2/2025, 2:04:53 AM | 2 | 22 | $3,314.712
DISR-00010 | STRIKE | LOW | Highway 101 | 8/2/2025, 6:04:53 AM | 8/2/2025, 10:04:53 PM | 7 | 98 | $14,970.541

## Impact Analysis
Metric | Value
Total Disruptions | 10
Active Disruptions | 6
Total Delayed Deliveries | 627
Total Additional Cost | $71,337.962
Affected Customers | 501
Average Resolution Time | 4.5 hours

## Mitigation Actions
Disruption ID | Action | Priority | Status | Responsible
DISR-00001 | Reroute affected vehicles | MEDIUM | In Progress | Operations Team
DISR-00001 | Notify customers of delays | MEDIUM | In Progress | Operations Team
DISR-00004 | Reroute affected vehicles | IMMEDIATE | In Progress | Operations Team
DISR-00004 | Notify customers of delays | IMMEDIATE | Planned | Operations Team
DISR-00004 | Deploy backup resources | IMMEDIATE | Planned | Operations Team
DISR-00005 | Reroute affected vehicles | IMMEDIATE | In Progress | Operations Team
DISR-00005 | Notify customers of delays | IMMEDIATE | Planned | Operations Team
DISR-00005 | Deploy backup resources | IMMEDIATE | Planned | Operations Team
DISR-00006 | Reroute affected vehicles | IMMEDIATE | In Progress | Operations Team
DISR-00006 | Notify customers of delays | IMMEDIATE | Planned | Operations Team
DISR-00009 | Reroute affected vehicles | HIGH | Planned | Operations Team
DISR-00009 | Notify customers of delays | HIGH | Planned | Operations Team
DISR-00010 | Reroute affected vehicles | MEDIUM | Planned | Operations Team
DISR-00010 | Notify customers of delays | MEDIUM | In Progress | Operations Team
DISR-00010 | Deploy backup resources | MEDIUM | Planned | Operations Team

## Historical Analysis
Month | Disruptions | Avg Resolution (hrs) | Total Cost
January | 12 | 4.2 | $45,000
February | 8 | 3.8 | $32,000
March | 15 | 5.1 | $58,000
April | 10 | 3.5 | $38,000