## Report Information
Property | Value
Report Name | Supply Chain Disruption Report
Description | Real-time disruption monitoring and mitigation
Generated By | Vanguard Disruption Manager
Use Case | supply-chain-disruption
Workflow ID | disruption-report
Generated At | 2025-08-03T13:01:08.484Z

## Active Disruptions
Disruption ID | Type | Severity | Location | Started | Est. Resolution | Affected Routes | Delayed Deliveries | Additional Cost
DISR-00001 | EQUIPMENT | MEDIUM | Highway 101 | 8/1/2025, 3:01:08 PM | 8/1/2025, 8:01:08 PM | 1 | 12 | $1,021.092
DISR-00002 | ACCIDENT | HIGH | Mexican Border | 8/1/2025, 10:01:08 PM | 8/2/2025, 9:01:08 PM | 4 | 24 | $4,283.809
DISR-00003 | WEATHER | CRITICAL | Port of LA | 8/1/2025, 11:01:08 PM | 8/2/2025, 2:01:08 PM | 8 | 112 | $6,936.733
DISR-00006 | STRIKE | CRITICAL | JFK Airport | 8/2/2025, 6:01:08 AM | 8/2/2025, 2:01:08 PM | 7 | 77 | $5,218.429
DISR-00007 | ACCIDENT | HIGH | JFK Airport | 8/2/2025, 12:01:08 AM | 8/2/2025, 7:01:08 PM | 5 | 50 | $6,846.796
DISR-00009 | ACCIDENT | MEDIUM | Port of LA | 8/2/2025, 11:01:08 AM | 8/3/2025, 3:01:08 AM | 1 | 14 | $2,124.753

## Impact Analysis
Metric | Value
Total Disruptions | 10
Active Disruptions | 6
Total Delayed Deliveries | 400
Total Additional Cost | $38,365.92
Affected Customers | 319
Average Resolution Time | 4.5 hours

## Mitigation Actions
Disruption ID | Action | Priority | Status | Responsible
DISR-00001 | Reroute affected vehicles | MEDIUM | In Progress | Operations Team
DISR-00001 | Notify customers of delays | MEDIUM | In Progress | Operations Team
DISR-00001 | Deploy backup resources | MEDIUM | Planned | Operations Team
DISR-00002 | Reroute affected vehicles | HIGH | Planned | Operations Team
DISR-00002 | Notify customers of delays | HIGH | In Progress | Operations Team
DISR-00002 | Deploy backup resources | HIGH | Planned | Operations Team
DISR-00003 | Reroute affected vehicles | IMMEDIATE | In Progress | Operations Team
DISR-00003 | Notify customers of delays | IMMEDIATE | Planned | Operations Team
DISR-00003 | Deploy backup resources | IMMEDIATE | In Progress | Operations Team
DISR-00006 | Reroute affected vehicles | IMMEDIATE | Planned | Operations Team
DISR-00006 | Notify customers of delays | IMMEDIATE | In Progress | Operations Team
DISR-00006 | Deploy backup resources | IMMEDIATE | Planned | Operations Team
DISR-00007 | Reroute affected vehicles | HIGH | Planned | Operations Team
DISR-00007 | Notify customers of delays | HIGH | Planned | Operations Team
DISR-00009 | Reroute affected vehicles | MEDIUM | In Progress | Operations Team
DISR-00009 | Notify customers of delays | MEDIUM | Planned | Operations Team
DISR-00009 | Deploy backup resources | MEDIUM | In Progress | Operations Team

## Historical Analysis
Month | Disruptions | Avg Resolution (hrs) | Total Cost
January | 12 | 4.2 | $45,000
February | 8 | 3.8 | $32,000
March | 15 | 5.1 | $58,000
April | 10 | 3.5 | $38,000