## Report Information
Property | Value
Report Name | Supply Chain Disruption Report
Description | Real-time disruption monitoring and mitigation
Generated By | Vanguard Disruption Manager
Use Case | supply-chain-disruption
Workflow ID | disruption-report
Generated At | 2025-08-03T13:00:37.697Z

## Active Disruptions
Disruption ID | Type | Severity | Location | Started | Est. Resolution | Affected Routes | Delayed Deliveries | Additional Cost
DISR-00001 | ACCIDENT | HIGH | Port of LA | 8/2/2025, 1:00:37 PM | 8/3/2025, 2:00:37 PM | 6 | 78 | $8,746.106
DISR-00007 | CUSTOMS | MEDIUM | Mexican Border | 8/3/2025, 5:00:37 AM | 8/3/2025, 1:00:37 PM | 4 | 24 | $3,062.008
DISR-00008 | EQUIPMENT | MEDIUM | Highway 101 | 8/1/2025, 3:00:37 PM | 8/2/2025, 8:00:37 AM | 6 | 60 | $8,103.85
DISR-00010 | STRIKE | MEDIUM | Mexican Border | 8/2/2025, 6:00:37 PM | 8/3/2025, 7:00:37 AM | 4 | 48 | $6,898.898

## Impact Analysis
Metric | Value
Total Disruptions | 10
Active Disruptions | 4
Total Delayed Deliveries | 483
Total Additional Cost | $66,171.62
Affected Customers | 386
Average Resolution Time | 4.5 hours

## Mitigation Actions
Disruption ID | Action | Priority | Status | Responsible
DISR-00001 | Reroute affected vehicles | HIGH | In Progress | Operations Team
DISR-00001 | Notify customers of delays | HIGH | In Progress | Operations Team
DISR-00001 | Deploy backup resources | HIGH | In Progress | Operations Team
DISR-00007 | Reroute affected vehicles | MEDIUM | In Progress | Operations Team
DISR-00007 | Notify customers of delays | MEDIUM | In Progress | Operations Team
DISR-00007 | Deploy backup resources | MEDIUM | Planned | Operations Team
DISR-00008 | Reroute affected vehicles | MEDIUM | Planned | Operations Team
DISR-00008 | Notify customers of delays | MEDIUM | In Progress | Operations Team
DISR-00008 | Deploy backup resources | MEDIUM | In Progress | Operations Team
DISR-00010 | Reroute affected vehicles | MEDIUM | In Progress | Operations Team
DISR-00010 | Notify customers of delays | MEDIUM | Planned | Operations Team
DISR-00010 | Deploy backup resources | MEDIUM | In Progress | Operations Team

## Historical Analysis
Month | Disruptions | Avg Resolution (hrs) | Total Cost
January | 12 | 4.2 | $45,000
February | 8 | 3.8 | $32,000
March | 15 | 5.1 | $58,000
April | 10 | 3.5 | $38,000