## Report Information
Property | Value
Report Name | Supply Chain Disruption Report
Description | Real-time disruption monitoring and mitigation
Generated By | Vanguard Disruption Manager
Use Case | supply-chain-disruption
Workflow ID | disruption-report
Generated At | 2025-08-03T13:06:37.123Z

## Active Disruptions
Disruption ID | Type | Severity | Location | Started | Est. Resolution | Affected Routes | Delayed Deliveries | Additional Cost
DISR-00001 | STRIKE | MEDIUM | Mexican Border | 8/2/2025, 12:06:37 PM | 8/3/2025, 3:06:37 AM | 10 | 50 | $6,809.205
DISR-00003 | TRAFFIC | CRITICAL | Port of LA | 8/3/2025, 6:06:37 AM | 8/3/2025, 12:06:37 PM | 8 | 48 | $6,253.582
DISR-00004 | ACCIDENT | MEDIUM | Chicago Hub | 8/3/2025, 5:06:37 AM | 8/3/2025, 1:06:37 PM | 3 | 30 | $2,353.485
DISR-00005 | WEATHER | CRITICAL | Port of LA | 8/2/2025, 9:06:37 AM | 8/2/2025, 2:06:37 PM | 1 | 6 | $934.476
DISR-00007 | TRAFFIC | CRITICAL | Port of LA | 8/2/2025, 11:06:37 AM | 8/3/2025, 6:06:37 AM | 4 | 56 | $7,900.687

## Impact Analysis
Metric | Value
Total Disruptions | 10
Active Disruptions | 5
Total Delayed Deliveries | 374
Total Additional Cost | $44,616.496
Affected Customers | 299
Average Resolution Time | 4.5 hours

## Mitigation Actions
Disruption ID | Action | Priority | Status | Responsible
DISR-00001 | Reroute affected vehicles | MEDIUM | In Progress | Operations Team
DISR-00001 | Notify customers of delays | MEDIUM | In Progress | Operations Team
DISR-00001 | Deploy backup resources | MEDIUM | In Progress | Operations Team
DISR-00003 | Reroute affected vehicles | IMMEDIATE | In Progress | Operations Team
DISR-00003 | Notify customers of delays | IMMEDIATE | Planned | Operations Team
DISR-00004 | Reroute affected vehicles | MEDIUM | In Progress | Operations Team
DISR-00004 | Notify customers of delays | MEDIUM | In Progress | Operations Team
DISR-00005 | Reroute affected vehicles | IMMEDIATE | Planned | Operations Team
DISR-00005 | Notify customers of delays | IMMEDIATE | In Progress | Operations Team
DISR-00005 | Deploy backup resources | IMMEDIATE | Planned | Operations Team
DISR-00007 | Reroute affected vehicles | IMMEDIATE | In Progress | Operations Team
DISR-00007 | Notify customers of delays | IMMEDIATE | Planned | Operations Team

## Historical Analysis
Month | Disruptions | Avg Resolution (hrs) | Total Cost
January | 12 | 4.2 | $45,000
February | 8 | 3.8 | $32,000
March | 15 | 5.1 | $58,000
April | 10 | 3.5 | $38,000