## Report Information
Property | Value
Report Name | Supply Chain Disruption Report
Description | Real-time disruption monitoring and mitigation
Generated By | Vanguard Disruption Manager
Use Case | supply-chain-disruption
Workflow ID | disruption-report
Generated At | 2025-08-03T13:04:23.176Z

## Active Disruptions
Disruption ID | Type | Severity | Location | Started | Est. Resolution | Affected Routes | Delayed Deliveries | Additional Cost
DISR-00003 | ACCIDENT | MEDIUM | Mexican Border | 8/2/2025, 7:04:23 PM | 8/3/2025, 5:04:23 AM | 3 | 30 | $4,082.731
DISR-00004 | WEATHER | CRITICAL | Port of LA | 8/2/2025, 10:04:23 PM | 8/3/2025, 1:04:23 PM | 3 | 21 | $3,127.798
DISR-00007 | TRAFFIC | CRITICAL | Highway 101 | 8/2/2025, 9:04:23 AM | 8/2/2025, 7:04:23 PM | 4 | 36 | $2,046.553
DISR-00008 | EQUIPMENT | MEDIUM | Chicago Hub | 8/2/2025, 2:04:23 PM | 8/2/2025, 4:04:23 PM | 4 | 44 | $2,954.698
DISR-00010 | WEATHER | LOW | JFK Airport | 8/1/2025, 5:04:23 PM | 8/1/2025, 8:04:23 PM | 6 | 48 | $5,338.96

## Impact Analysis
Metric | Value
Total Disruptions | 10
Active Disruptions | 5
Total Delayed Deliveries | 333
Total Additional Cost | $43,536.986
Affected Customers | 266
Average Resolution Time | 4.5 hours

## Mitigation Actions
Disruption ID | Action | Priority | Status | Responsible
DISR-00003 | Reroute affected vehicles | MEDIUM | In Progress | Operations Team
DISR-00003 | Notify customers of delays | MEDIUM | In Progress | Operations Team
DISR-00003 | Deploy backup resources | MEDIUM | Planned | Operations Team
DISR-00004 | Reroute affected vehicles | IMMEDIATE | In Progress | Operations Team
DISR-00004 | Notify customers of delays | IMMEDIATE | In Progress | Operations Team
DISR-00004 | Deploy backup resources | IMMEDIATE | In Progress | Operations Team
DISR-00007 | Reroute affected vehicles | IMMEDIATE | Planned | Operations Team
DISR-00007 | Notify customers of delays | IMMEDIATE | In Progress | Operations Team
DISR-00007 | Deploy backup resources | IMMEDIATE | In Progress | Operations Team
DISR-00008 | Reroute affected vehicles | MEDIUM | Planned | Operations Team
DISR-00008 | Notify customers of delays | MEDIUM | In Progress | Operations Team
DISR-00008 | Deploy backup resources | MEDIUM | In Progress | Operations Team
DISR-00010 | Reroute affected vehicles | MEDIUM | In Progress | Operations Team
DISR-00010 | Notify customers of delays | MEDIUM | In Progress | Operations Team
DISR-00010 | Deploy backup resources | MEDIUM | Planned | Operations Team

## Historical Analysis
Month | Disruptions | Avg Resolution (hrs) | Total Cost
January | 12 | 4.2 | $45,000
February | 8 | 3.8 | $32,000
March | 15 | 5.1 | $58,000
April | 10 | 3.5 | $38,000