## Report Information
Property | Value
Report Name | Supply Chain Disruption Report
Description | Real-time disruption monitoring and mitigation
Generated By | Vanguard Disruption Manager
Use Case | supply-chain-disruption
Workflow ID | disruption-report
Generated At | 2025-08-03T13:01:00.144Z

## Active Disruptions
Disruption ID | Type | Severity | Location | Started | Est. Resolution | Affected Routes | Delayed Deliveries | Additional Cost
DISR-00003 | EQUIPMENT | MEDIUM | Chicago Hub | 8/1/2025, 12:01:00 PM | 8/2/2025, 8:01:00 AM | 7 | 35 | $3,766.541
DISR-00004 | ACCIDENT | CRITICAL | Chicago Hub | 8/3/2025, 4:01:00 AM | 8/3/2025, 7:01:00 PM | 6 | 72 | $6,937.685
DISR-00005 | STRIKE | HIGH | Highway 101 | 8/2/2025, 8:01:00 AM | 8/3/2025, 9:01:00 AM | 8 | 88 | $10,016.749
DISR-00006 | EQUIPMENT | HIGH | Chicago Hub | 8/1/2025, 4:01:00 PM | 8/1/2025, 11:01:00 PM | 3 | 18 | $1,399.817
DISR-00007 | ACCIDENT | HIGH | Port of LA | 8/2/2025, 1:01:00 AM | 8/2/2025, 4:01:00 PM | 9 | 126 | $12,959.202

## Impact Analysis
Metric | Value
Total Disruptions | 10
Active Disruptions | 5
Total Delayed Deliveries | 677
Total Additional Cost | $75,091.961
Affected Customers | 541
Average Resolution Time | 4.5 hours

## Mitigation Actions
Disruption ID | Action | Priority | Status | Responsible
DISR-00003 | Reroute affected vehicles | MEDIUM | In Progress | Operations Team
DISR-00003 | Notify customers of delays | MEDIUM | In Progress | Operations Team
DISR-00003 | Deploy backup resources | MEDIUM | In Progress | Operations Team
DISR-00004 | Reroute affected vehicles | IMMEDIATE | In Progress | Operations Team
DISR-00004 | Notify customers of delays | IMMEDIATE | Planned | Operations Team
DISR-00004 | Deploy backup resources | IMMEDIATE | Planned | Operations Team
DISR-00005 | Reroute affected vehicles | HIGH | In Progress | Operations Team
DISR-00005 | Notify customers of delays | HIGH | In Progress | Operations Team
DISR-00005 | Deploy backup resources | HIGH | Planned | Operations Team
DISR-00006 | Reroute affected vehicles | HIGH | In Progress | Operations Team
DISR-00006 | Notify customers of delays | HIGH | In Progress | Operations Team
DISR-00007 | Reroute affected vehicles | HIGH | Planned | Operations Team
DISR-00007 | Notify customers of delays | HIGH | Planned | Operations Team
DISR-00007 | Deploy backup resources | HIGH | In Progress | Operations Team

## Historical Analysis
Month | Disruptions | Avg Resolution (hrs) | Total Cost
January | 12 | 4.2 | $45,000
February | 8 | 3.8 | $32,000
March | 15 | 5.1 | $58,000
April | 10 | 3.5 | $38,000