## Report Information
Property | Value
Report Name | Supply Chain Disruption Report
Description | Real-time disruption monitoring and mitigation
Generated By | Vanguard Disruption Manager
Use Case | supply-chain-disruption
Workflow ID | disruption-report
Generated At | 2025-08-03T13:02:47.215Z

## Active Disruptions
Disruption ID | Type | Severity | Location | Started | Est. Resolution | Affected Routes | Delayed Deliveries | Additional Cost
DISR-00005 | STRIKE | HIGH | Highway 101 | 8/1/2025, 4:02:47 PM | 8/1/2025, 11:02:47 PM | 5 | 70 | $5,170.725
DISR-00007 | EQUIPMENT | CRITICAL | Chicago Hub | 8/3/2025, 1:02:47 AM | 8/4/2025, 1:02:47 AM | 2 | 12 | $1,428.587
DISR-00008 | EQUIPMENT | HIGH | Chicago Hub | 8/2/2025, 11:02:47 PM | 8/3/2025, 4:02:47 AM | 1 | 11 | $685.674
DISR-00010 | WEATHER | MEDIUM | Highway 101 | 8/1/2025, 9:02:47 PM | 8/2/2025, 6:02:47 AM | 4 | 56 | $5,235.045

## Impact Analysis
Metric | Value
Total Disruptions | 10
Active Disruptions | 4
Total Delayed Deliveries | 381
Total Additional Cost | $50,546.689
Affected Customers | 304
Average Resolution Time | 4.5 hours

## Mitigation Actions
Disruption ID | Action | Priority | Status | Responsible
DISR-00005 | Reroute affected vehicles | HIGH | In Progress | Operations Team
DISR-00005 | Notify customers of delays | HIGH | Planned | Operations Team
DISR-00005 | Deploy backup resources | HIGH | Planned | Operations Team
DISR-00007 | Reroute affected vehicles | IMMEDIATE | Planned | Operations Team
DISR-00007 | Notify customers of delays | IMMEDIATE | In Progress | Operations Team
DISR-00008 | Reroute affected vehicles | HIGH | In Progress | Operations Team
DISR-00008 | Notify customers of delays | HIGH | In Progress | Operations Team
DISR-00010 | Reroute affected vehicles | MEDIUM | In Progress | Operations Team
DISR-00010 | Notify customers of delays | MEDIUM | In Progress | Operations Team
DISR-00010 | Deploy backup resources | MEDIUM | In Progress | Operations Team

## Historical Analysis
Month | Disruptions | Avg Resolution (hrs) | Total Cost
January | 12 | 4.2 | $45,000
February | 8 | 3.8 | $32,000
March | 15 | 5.1 | $58,000
April | 10 | 3.5 | $38,000