## Report Information
Property | Value
Report Name | Supply Chain Disruption Report
Description | Real-time disruption monitoring and mitigation
Generated By | Vanguard Disruption Manager
Use Case | supply-chain-disruption
Workflow ID | disruption-report
Generated At | 2025-08-03T13:04:39.371Z

## Active Disruptions
Disruption ID | Type | Severity | Location | Started | Est. Resolution | Affected Routes | Delayed Deliveries | Additional Cost
DISR-00002 | ACCIDENT | CRITICAL | Highway 101 | 8/1/2025, 9:04:39 AM | 8/2/2025, 10:04:39 AM | 8 | 112 | $16,277.576
DISR-00003 | CUSTOMS | LOW | Port of LA | 8/1/2025, 11:04:39 AM | 8/2/2025, 12:04:39 AM | 5 | 40 | $4,086.34
DISR-00005 | WEATHER | LOW | Highway 101 | 8/2/2025, 6:04:39 AM | 8/2/2025, 8:04:39 AM | 1 | 11 | $742.397
DISR-00006 | EQUIPMENT | LOW | Chicago Hub | 8/2/2025, 10:04:39 AM | 8/3/2025, 3:04:39 AM | 2 | 22 | $2,889.485
DISR-00008 | TRAFFIC | CRITICAL | Port of LA | 8/1/2025, 10:04:39 PM | 8/2/2025, 2:04:39 PM | 6 | 54 | $4,458.681

## Impact Analysis
Metric | Value
Total Disruptions | 10
Active Disruptions | 5
Total Delayed Deliveries | 605
Total Additional Cost | $80,966.142
Affected Customers | 484
Average Resolution Time | 4.5 hours

## Mitigation Actions
Disruption ID | Action | Priority | Status | Responsible
DISR-00002 | Reroute affected vehicles | IMMEDIATE | Planned | Operations Team
DISR-00002 | Notify customers of delays | IMMEDIATE | In Progress | Operations Team
DISR-00003 | Reroute affected vehicles | MEDIUM | In Progress | Operations Team
DISR-00003 | Notify customers of delays | MEDIUM | In Progress | Operations Team
DISR-00003 | Deploy backup resources | MEDIUM | Planned | Operations Team
DISR-00005 | Reroute affected vehicles | MEDIUM | In Progress | Operations Team
DISR-00005 | Notify customers of delays | MEDIUM | Planned | Operations Team
DISR-00005 | Deploy backup resources | MEDIUM | In Progress | Operations Team
DISR-00006 | Reroute affected vehicles | MEDIUM | Planned | Operations Team
DISR-00006 | Notify customers of delays | MEDIUM | Planned | Operations Team
DISR-00008 | Reroute affected vehicles | IMMEDIATE | Planned | Operations Team
DISR-00008 | Notify customers of delays | IMMEDIATE | In Progress | Operations Team
DISR-00008 | Deploy backup resources | IMMEDIATE | Planned | Operations Team

## Historical Analysis
Month | Disruptions | Avg Resolution (hrs) | Total Cost
January | 12 | 4.2 | $45,000
February | 8 | 3.8 | $32,000
March | 15 | 5.1 | $58,000
April | 10 | 3.5 | $38,000