## Report Information
Property | Value
Report Name | Supply Chain Disruption Report
Description | Real-time disruption monitoring and mitigation
Generated By | Vanguard Disruption Manager
Use Case | supply-chain-disruption
Workflow ID | disruption-report
Generated At | 2025-08-03T13:06:18.832Z

## Active Disruptions
Disruption ID | Type | Severity | Location | Started | Est. Resolution | Affected Routes | Delayed Deliveries | Additional Cost
DISR-00003 | CUSTOMS | CRITICAL | Chicago Hub | 8/1/2025, 1:06:18 PM | 8/2/2025, 10:06:18 AM | 10 | 50 | $6,116.281
DISR-00004 | TRAFFIC | HIGH | Highway 101 | 8/1/2025, 1:06:18 PM | 8/2/2025, 2:06:18 AM | 9 | 72 | $13,626.069
DISR-00006 | WEATHER | HIGH | Mexican Border | 8/3/2025, 6:06:18 AM | 8/3/2025, 1:06:18 PM | 10 | 70 | $11,697.952
DISR-00010 | CUSTOMS | CRITICAL | Mexican Border | 8/2/2025, 11:06:18 AM | 8/3/2025, 6:06:18 AM | 4 | 32 | $3,573.92

## Impact Analysis
Metric | Value
Total Disruptions | 10
Active Disruptions | 4
Total Delayed Deliveries | 581
Total Additional Cost | $76,608.723
Affected Customers | 464
Average Resolution Time | 4.5 hours

## Mitigation Actions
Disruption ID | Action | Priority | Status | Responsible
DISR-00003 | Reroute affected vehicles | IMMEDIATE | Planned | Operations Team
DISR-00003 | Notify customers of delays | IMMEDIATE | In Progress | Operations Team
DISR-00004 | Reroute affected vehicles | HIGH | Planned | Operations Team
DISR-00004 | Notify customers of delays | HIGH | Planned | Operations Team
DISR-00006 | Reroute affected vehicles | HIGH | In Progress | Operations Team
DISR-00006 | Notify customers of delays | HIGH | In Progress | Operations Team
DISR-00010 | Reroute affected vehicles | IMMEDIATE | Planned | Operations Team
DISR-00010 | Notify customers of delays | IMMEDIATE | Planned | Operations Team
DISR-00010 | Deploy backup resources | IMMEDIATE | In Progress | Operations Team

## Historical Analysis
Month | Disruptions | Avg Resolution (hrs) | Total Cost
January | 12 | 4.2 | $45,000
February | 8 | 3.8 | $32,000
March | 15 | 5.1 | $58,000
April | 10 | 3.5 | $38,000