## Report Information
Property | Value
Report Name | Supply Chain Disruption Report
Description | Real-time disruption monitoring and mitigation
Generated By | Vanguard Disruption Manager
Use Case | supply-chain-disruption
Workflow ID | disruption-report
Generated At | 2025-08-03T13:01:46.238Z

## Active Disruptions
Disruption ID | Type | Severity | Location | Started | Est. Resolution | Affected Routes | Delayed Deliveries | Additional Cost
DISR-00002 | EQUIPMENT | HIGH | Port of LA | 8/1/2025, 11:01:46 AM | 8/2/2025, 3:01:46 AM | 5 | 35 | $5,507.544
DISR-00008 | STRIKE | CRITICAL | Chicago Hub | 8/2/2025, 3:01:46 PM | 8/3/2025, 3:01:46 AM | 8 | 96 | $16,783.184
DISR-00009 | STRIKE | LOW | JFK Airport | 8/2/2025, 11:01:46 PM | 8/3/2025, 1:01:46 PM | 8 | 56 | $6,178.16
DISR-00010 | CUSTOMS | CRITICAL | JFK Airport | 8/2/2025, 9:01:46 PM | 8/3/2025, 12:01:46 AM | 7 | 77 | $13,742.112

## Impact Analysis
Metric | Value
Total Disruptions | 10
Active Disruptions | 4
Total Delayed Deliveries | 563
Total Additional Cost | $76,354.53
Affected Customers | 450
Average Resolution Time | 4.5 hours

## Mitigation Actions
Disruption ID | Action | Priority | Status | Responsible
DISR-00002 | Reroute affected vehicles | HIGH | In Progress | Operations Team
DISR-00002 | Notify customers of delays | HIGH | Planned | Operations Team
DISR-00008 | Reroute affected vehicles | IMMEDIATE | Planned | Operations Team
DISR-00008 | Notify customers of delays | IMMEDIATE | In Progress | Operations Team
DISR-00008 | Deploy backup resources | IMMEDIATE | Planned | Operations Team
DISR-00009 | Reroute affected vehicles | MEDIUM | Planned | Operations Team
DISR-00009 | Notify customers of delays | MEDIUM | In Progress | Operations Team
DISR-00009 | Deploy backup resources | MEDIUM | Planned | Operations Team
DISR-00010 | Reroute affected vehicles | IMMEDIATE | Planned | Operations Team
DISR-00010 | Notify customers of delays | IMMEDIATE | Planned | Operations Team
DISR-00010 | Deploy backup resources | IMMEDIATE | In Progress | Operations Team

## Historical Analysis
Month | Disruptions | Avg Resolution (hrs) | Total Cost
January | 12 | 4.2 | $45,000
February | 8 | 3.8 | $32,000
March | 15 | 5.1 | $58,000
April | 10 | 3.5 | $38,000