## Report Information
Property | Value
Report Name | Supply Chain Disruption Report
Description | Real-time disruption monitoring and mitigation
Generated By | Vanguard Disruption Manager
Use Case | supply-chain-disruption
Workflow ID | disruption-report
Generated At | 2025-08-03T13:02:49.692Z

## Active Disruptions
Disruption ID | Type | Severity | Location | Started | Est. Resolution | Affected Routes | Delayed Deliveries | Additional Cost
DISR-00001 | TRAFFIC | CRITICAL | Mexican Border | 8/1/2025, 11:02:49 PM | 8/2/2025, 9:02:49 PM | 1 | 13 | $1,796.296
DISR-00002 | ACCIDENT | HIGH | Highway 101 | 8/2/2025, 11:02:49 AM | 8/2/2025, 9:02:49 PM | 7 | 98 | $5,897.065
DISR-00003 | CUSTOMS | CRITICAL | JFK Airport | 8/3/2025, 1:02:49 AM | 8/3/2025, 4:02:49 PM | 2 | 10 | $569.11
DISR-00005 | STRIKE | HIGH | Mexican Border | 8/1/2025, 4:02:49 PM | 8/2/2025, 12:02:49 AM | 10 | 120 | $7,766.559

## Impact Analysis
Metric | Value
Total Disruptions | 10
Active Disruptions | 4
Total Delayed Deliveries | 626
Total Additional Cost | $51,691.268
Affected Customers | 500
Average Resolution Time | 4.5 hours

## Mitigation Actions
Disruption ID | Action | Priority | Status | Responsible
DISR-00001 | Reroute affected vehicles | IMMEDIATE | In Progress | Operations Team
DISR-00001 | Notify customers of delays | IMMEDIATE | In Progress | Operations Team
DISR-00001 | Deploy backup resources | IMMEDIATE | In Progress | Operations Team
DISR-00002 | Reroute affected vehicles | HIGH | Planned | Operations Team
DISR-00002 | Notify customers of delays | HIGH | In Progress | Operations Team
DISR-00002 | Deploy backup resources | HIGH | In Progress | Operations Team
DISR-00003 | Reroute affected vehicles | IMMEDIATE | Planned | Operations Team
DISR-00003 | Notify customers of delays | IMMEDIATE | In Progress | Operations Team
DISR-00003 | Deploy backup resources | IMMEDIATE | Planned | Operations Team
DISR-00005 | Reroute affected vehicles | HIGH | Planned | Operations Team
DISR-00005 | Notify customers of delays | HIGH | Planned | Operations Team
DISR-00005 | Deploy backup resources | HIGH | Planned | Operations Team

## Historical Analysis
Month | Disruptions | Avg Resolution (hrs) | Total Cost
January | 12 | 4.2 | $45,000
February | 8 | 3.8 | $32,000
March | 15 | 5.1 | $58,000
April | 10 | 3.5 | $38,000