## Report Information
Property | Value
Report Name | Supply Chain Disruption Report
Description | Real-time disruption monitoring and mitigation
Generated By | Vanguard Disruption Manager
Use Case | supply-chain-disruption
Workflow ID | disruption-report
Generated At | 2025-08-03T13:07:38.406Z

## Active Disruptions
Disruption ID | Type | Severity | Location | Started | Est. Resolution | Affected Routes | Delayed Deliveries | Additional Cost
DISR-00001 | STRIKE | CRITICAL | Port of LA | 8/2/2025, 7:07:38 AM | 8/3/2025, 5:07:38 AM | 5 | 45 | $5,327.399
DISR-00003 | CUSTOMS | CRITICAL | Port of LA | 8/2/2025, 6:07:38 AM | 8/2/2025, 2:07:38 PM | 2 | 26 | $4,636.489
DISR-00004 | ACCIDENT | HIGH | Port of LA | 8/2/2025, 5:07:38 PM | 8/3/2025, 2:07:38 PM | 10 | 100 | $14,084.716
DISR-00005 | CUSTOMS | CRITICAL | Mexican Border | 8/3/2025, 6:07:38 AM | 8/3/2025, 6:07:38 PM | 10 | 70 | $7,970.902
DISR-00006 | EQUIPMENT | LOW | JFK Airport | 8/3/2025, 1:07:38 AM | 8/3/2025, 11:07:38 AM | 8 | 72 | $7,696.958
DISR-00008 | WEATHER | MEDIUM | Highway 101 | 8/3/2025, 5:07:38 AM | 8/4/2025, 1:07:38 AM | 5 | 25 | $4,047.141
DISR-00009 | STRIKE | MEDIUM | Chicago Hub | 8/1/2025, 5:07:38 PM | 8/1/2025, 7:07:38 PM | 4 | 20 | $1,898.515

## Impact Analysis
Metric | Value
Total Disruptions | 10
Active Disruptions | 7
Total Delayed Deliveries | 566
Total Additional Cost | $69,108.311
Affected Customers | 452
Average Resolution Time | 4.5 hours

## Mitigation Actions
Disruption ID | Action | Priority | Status | Responsible
DISR-00001 | Reroute affected vehicles | IMMEDIATE | Planned | Operations Team
DISR-00001 | Notify customers of delays | IMMEDIATE | In Progress | Operations Team
DISR-00001 | Deploy backup resources | IMMEDIATE | Planned | Operations Team
DISR-00003 | Reroute affected vehicles | IMMEDIATE | Planned | Operations Team
DISR-00003 | Notify customers of delays | IMMEDIATE | Planned | Operations Team
DISR-00003 | Deploy backup resources | IMMEDIATE | In Progress | Operations Team
DISR-00004 | Reroute affected vehicles | HIGH | In Progress | Operations Team
DISR-00004 | Notify customers of delays | HIGH | In Progress | Operations Team
DISR-00005 | Reroute affected vehicles | IMMEDIATE | In Progress | Operations Team
DISR-00005 | Notify customers of delays | IMMEDIATE | In Progress | Operations Team
DISR-00006 | Reroute affected vehicles | MEDIUM | In Progress | Operations Team
DISR-00006 | Notify customers of delays | MEDIUM | Planned | Operations Team
DISR-00008 | Reroute affected vehicles | MEDIUM | Planned | Operations Team
DISR-00008 | Notify customers of delays | MEDIUM | Planned | Operations Team
DISR-00008 | Deploy backup resources | MEDIUM | In Progress | Operations Team
DISR-00009 | Reroute affected vehicles | MEDIUM | Planned | Operations Team
DISR-00009 | Notify customers of delays | MEDIUM | Planned | Operations Team

## Historical Analysis
Month | Disruptions | Avg Resolution (hrs) | Total Cost
January | 12 | 4.2 | $45,000
February | 8 | 3.8 | $32,000
March | 15 | 5.1 | $58,000
April | 10 | 3.5 | $38,000