## Report Information
Property | Value
Report Name | Supply Chain Disruption Report
Description | Real-time disruption monitoring and mitigation
Generated By | Vanguard Disruption Manager
Use Case | supply-chain-disruption
Workflow ID | disruption-report
Generated At | 2025-08-03T13:01:35.770Z

## Active Disruptions
Disruption ID | Type | Severity | Location | Started | Est. Resolution | Affected Routes | Delayed Deliveries | Additional Cost
DISR-00002 | CUSTOMS | HIGH | JFK Airport | 8/2/2025, 3:01:35 PM | 8/3/2025, 7:01:35 AM | 7 | 98 | $9,574.784
DISR-00007 | WEATHER | MEDIUM | Chicago Hub | 8/2/2025, 6:01:35 PM | 8/3/2025, 1:01:35 PM | 3 | 15 | $2,868.221
DISR-00009 | WEATHER | CRITICAL | JFK Airport | 8/2/2025, 2:01:35 AM | 8/2/2025, 9:01:35 PM | 10 | 110 | $21,754.266
DISR-00010 | TRAFFIC | CRITICAL | Port of LA | 8/1/2025, 4:01:35 PM | 8/1/2025, 7:01:35 PM | 8 | 112 | $9,161.597

## Impact Analysis
Metric | Value
Total Disruptions | 10
Active Disruptions | 4
Total Delayed Deliveries | 567
Total Additional Cost | $77,341.319
Affected Customers | 453
Average Resolution Time | 4.5 hours

## Mitigation Actions
Disruption ID | Action | Priority | Status | Responsible
DISR-00002 | Reroute affected vehicles | HIGH | Planned | Operations Team
DISR-00002 | Notify customers of delays | HIGH | In Progress | Operations Team
DISR-00002 | Deploy backup resources | HIGH | In Progress | Operations Team
DISR-00007 | Reroute affected vehicles | MEDIUM | Planned | Operations Team
DISR-00007 | Notify customers of delays | MEDIUM | Planned | Operations Team
DISR-00007 | Deploy backup resources | MEDIUM | Planned | Operations Team
DISR-00009 | Reroute affected vehicles | IMMEDIATE | In Progress | Operations Team
DISR-00009 | Notify customers of delays | IMMEDIATE | In Progress | Operations Team
DISR-00010 | Reroute affected vehicles | IMMEDIATE | Planned | Operations Team
DISR-00010 | Notify customers of delays | IMMEDIATE | Planned | Operations Team
DISR-00010 | Deploy backup resources | IMMEDIATE | In Progress | Operations Team

## Historical Analysis
Month | Disruptions | Avg Resolution (hrs) | Total Cost
January | 12 | 4.2 | $45,000
February | 8 | 3.8 | $32,000
March | 15 | 5.1 | $58,000
April | 10 | 3.5 | $38,000