## Report Information
Property | Value
Report Name | Supply Chain Disruption Report
Description | Real-time disruption monitoring and mitigation
Generated By | Vanguard Disruption Manager
Use Case | supply-chain-disruption
Workflow ID | disruption-report
Generated At | 2025-08-03T13:03:48.072Z

## Active Disruptions
Disruption ID | Type | Severity | Location | Started | Est. Resolution | Affected Routes | Delayed Deliveries | Additional Cost
DISR-00001 | WEATHER | CRITICAL | JFK Airport | 8/2/2025, 10:03:48 PM | 8/3/2025, 8:03:48 AM | 1 | 5 | $435.743
DISR-00002 | STRIKE | CRITICAL | Port of LA | 8/1/2025, 8:03:48 PM | 8/2/2025, 5:03:48 PM | 2 | 20 | $2,540.068
DISR-00004 | CUSTOMS | LOW | Port of LA | 8/2/2025, 4:03:48 PM | 8/3/2025, 4:03:48 AM | 6 | 84 | $14,779.701
DISR-00006 | ACCIDENT | HIGH | Chicago Hub | 8/3/2025, 8:03:48 AM | 8/3/2025, 5:03:48 PM | 3 | 27 | $2,329.045
DISR-00007 | EQUIPMENT | MEDIUM | Port of LA | 8/1/2025, 11:03:48 PM | 8/2/2025, 7:03:48 AM | 6 | 36 | $5,882.428
DISR-00009 | WEATHER | HIGH | Highway 101 | 8/3/2025, 6:03:48 AM | 8/3/2025, 11:03:48 AM | 2 | 16 | $2,620.416

## Impact Analysis
Metric | Value
Total Disruptions | 10
Active Disruptions | 6
Total Delayed Deliveries | 315
Total Additional Cost | $44,804.03
Affected Customers | 252
Average Resolution Time | 4.5 hours

## Mitigation Actions
Disruption ID | Action | Priority | Status | Responsible
DISR-00001 | Reroute affected vehicles | IMMEDIATE | Planned | Operations Team
DISR-00001 | Notify customers of delays | IMMEDIATE | In Progress | Operations Team
DISR-00002 | Reroute affected vehicles | IMMEDIATE | Planned | Operations Team
DISR-00002 | Notify customers of delays | IMMEDIATE | Planned | Operations Team
DISR-00004 | Reroute affected vehicles | MEDIUM | In Progress | Operations Team
DISR-00004 | Notify customers of delays | MEDIUM | Planned | Operations Team
DISR-00004 | Deploy backup resources | MEDIUM | Planned | Operations Team
DISR-00006 | Reroute affected vehicles | HIGH | Planned | Operations Team
DISR-00006 | Notify customers of delays | HIGH | In Progress | Operations Team
DISR-00006 | Deploy backup resources | HIGH | In Progress | Operations Team
DISR-00007 | Reroute affected vehicles | MEDIUM | In Progress | Operations Team
DISR-00007 | Notify customers of delays | MEDIUM | In Progress | Operations Team
DISR-00007 | Deploy backup resources | MEDIUM | In Progress | Operations Team
DISR-00009 | Reroute affected vehicles | HIGH | In Progress | Operations Team
DISR-00009 | Notify customers of delays | HIGH | Planned | Operations Team
DISR-00009 | Deploy backup resources | HIGH | In Progress | Operations Team

## Historical Analysis
Month | Disruptions | Avg Resolution (hrs) | Total Cost
January | 12 | 4.2 | $45,000
February | 8 | 3.8 | $32,000
March | 15 | 5.1 | $58,000
April | 10 | 3.5 | $38,000