## Report Information
Property | Value
Report Name | Supply Chain Disruption Report
Description | Real-time disruption monitoring and mitigation
Generated By | Vanguard Disruption Manager
Use Case | supply-chain-disruption
Workflow ID | disruption-report
Generated At | 2025-08-03T13:04:09.350Z

## Active Disruptions
Disruption ID | Type | Severity | Location | Started | Est. Resolution | Affected Routes | Delayed Deliveries | Additional Cost
DISR-00001 | WEATHER | CRITICAL | JFK Airport | 8/1/2025, 9:04:09 PM | 8/2/2025, 7:04:09 PM | 4 | 28 | $4,013.332
DISR-00007 | EQUIPMENT | LOW | Port of LA | 8/1/2025, 9:04:09 PM | 8/2/2025, 1:04:09 AM | 7 | 91 | $15,798.08
DISR-00009 | CUSTOMS | HIGH | Highway 101 | 8/2/2025, 5:04:09 AM | 8/2/2025, 7:04:09 PM | 2 | 18 | $2,297.624

## Impact Analysis
Metric | Value
Total Disruptions | 10
Active Disruptions | 3
Total Delayed Deliveries | 484
Total Additional Cost | $74,667.115
Affected Customers | 387
Average Resolution Time | 4.5 hours

## Mitigation Actions
Disruption ID | Action | Priority | Status | Responsible
DISR-00001 | Reroute affected vehicles | IMMEDIATE | Planned | Operations Team
DISR-00001 | Notify customers of delays | IMMEDIATE | In Progress | Operations Team
DISR-00007 | Reroute affected vehicles | MEDIUM | In Progress | Operations Team
DISR-00007 | Notify customers of delays | MEDIUM | Planned | Operations Team
DISR-00009 | Reroute affected vehicles | HIGH | Planned | Operations Team
DISR-00009 | Notify customers of delays | HIGH | In Progress | Operations Team

## Historical Analysis
Month | Disruptions | Avg Resolution (hrs) | Total Cost
January | 12 | 4.2 | $45,000
February | 8 | 3.8 | $32,000
March | 15 | 5.1 | $58,000
April | 10 | 3.5 | $38,000