## Report Information
Property | Value
Report Name | Supply Chain Disruption Report
Description | Real-time disruption monitoring and mitigation
Generated By | Vanguard Disruption Manager
Use Case | supply-chain-disruption
Workflow ID | disruption-report
Generated At | 2025-08-03T13:03:21.725Z

## Active Disruptions
Disruption ID | Type | Severity | Location | Started | Est. Resolution | Affected Routes | Delayed Deliveries | Additional Cost
DISR-00002 | STRIKE | HIGH | Port of LA | 8/1/2025, 3:03:21 PM | 8/2/2025, 1:03:21 AM | 8 | 56 | $5,916.279
DISR-00003 | ACCIDENT | CRITICAL | Highway 101 | 8/2/2025, 11:03:21 AM | 8/2/2025, 11:03:21 PM | 7 | 77 | $13,076.934
DISR-00004 | EQUIPMENT | HIGH | Chicago Hub | 8/1/2025, 11:03:21 AM | 8/1/2025, 1:03:21 PM | 10 | 120 | $9,684.112
DISR-00005 | CUSTOMS | MEDIUM | Port of LA | 8/2/2025, 7:03:21 PM | 8/3/2025, 12:03:21 PM | 8 | 112 | $15,512.088
DISR-00006 | CUSTOMS | MEDIUM | Port of LA | 8/2/2025, 5:03:21 AM | 8/2/2025, 11:03:21 AM | 4 | 36 | $3,543.033
DISR-00007 | EQUIPMENT | LOW | Mexican Border | 8/1/2025, 7:03:21 PM | 8/1/2025, 9:03:21 PM | 6 | 30 | $3,927.52
DISR-00010 | EQUIPMENT | LOW | Mexican Border | 8/2/2025, 11:03:21 PM | 8/3/2025, 10:03:21 PM | 1 | 9 | $1,398.147

## Impact Analysis
Metric | Value
Total Disruptions | 10
Active Disruptions | 7
Total Delayed Deliveries | 576
Total Additional Cost | $73,255.67
Affected Customers | 460
Average Resolution Time | 4.5 hours

## Mitigation Actions
Disruption ID | Action | Priority | Status | Responsible
DISR-00002 | Reroute affected vehicles | HIGH | Planned | Operations Team
DISR-00002 | Notify customers of delays | HIGH | In Progress | Operations Team
DISR-00003 | Reroute affected vehicles | IMMEDIATE | In Progress | Operations Team
DISR-00003 | Notify customers of delays | IMMEDIATE | Planned | Operations Team
DISR-00003 | Deploy backup resources | IMMEDIATE | In Progress | Operations Team
DISR-00004 | Reroute affected vehicles | HIGH | Planned | Operations Team
DISR-00004 | Notify customers of delays | HIGH | In Progress | Operations Team
DISR-00004 | Deploy backup resources | HIGH | Planned | Operations Team
DISR-00005 | Reroute affected vehicles | MEDIUM | In Progress | Operations Team
DISR-00005 | Notify customers of delays | MEDIUM | Planned | Operations Team
DISR-00005 | Deploy backup resources | MEDIUM | In Progress | Operations Team
DISR-00006 | Reroute affected vehicles | MEDIUM | In Progress | Operations Team
DISR-00006 | Notify customers of delays | MEDIUM | Planned | Operations Team
DISR-00006 | Deploy backup resources | MEDIUM | In Progress | Operations Team
DISR-00007 | Reroute affected vehicles | MEDIUM | Planned | Operations Team
DISR-00007 | Notify customers of delays | MEDIUM | In Progress | Operations Team
DISR-00010 | Reroute affected vehicles | MEDIUM | In Progress | Operations Team
DISR-00010 | Notify customers of delays | MEDIUM | In Progress | Operations Team

## Historical Analysis
Month | Disruptions | Avg Resolution (hrs) | Total Cost
January | 12 | 4.2 | $45,000
February | 8 | 3.8 | $32,000
March | 15 | 5.1 | $58,000
April | 10 | 3.5 | $38,000