## Report Information
Property | Value
Report Name | Supply Chain Disruption Report
Description | Real-time disruption monitoring and mitigation
Generated By | Vanguard Disruption Manager
Use Case | supply-chain-disruption
Workflow ID | disruption-report
Generated At | 2025-08-03T13:00:29.834Z

## Active Disruptions
Disruption ID | Type | Severity | Location | Started | Est. Resolution | Affected Routes | Delayed Deliveries | Additional Cost
DISR-00003 | STRIKE | CRITICAL | JFK Airport | 8/2/2025, 11:00:29 PM | 8/3/2025, 6:00:29 AM | 9 | 90 | $5,945.705

## Impact Analysis
Metric | Value
Total Disruptions | 10
Active Disruptions | 1
Total Delayed Deliveries | 490
Total Additional Cost | $66,176.761
Affected Customers | 392
Average Resolution Time | 4.5 hours

## Mitigation Actions
Disruption ID | Action | Priority | Status | Responsible
DISR-00003 | Reroute affected vehicles | IMMEDIATE | Planned | Operations Team
DISR-00003 | Notify customers of delays | IMMEDIATE | In Progress | Operations Team

## Historical Analysis
Month | Disruptions | Avg Resolution (hrs) | Total Cost
January | 12 | 4.2 | $45,000
February | 8 | 3.8 | $32,000
March | 15 | 5.1 | $58,000
April | 10 | 3.5 | $38,000