## Report Information
Property | Value
Report Name | Supply Chain Disruption Report
Description | Real-time disruption monitoring and mitigation
Generated By | Vanguard Disruption Manager
Use Case | supply-chain-disruption
Workflow ID | disruption-report
Generated At | 2025-08-03T13:00:35.213Z

## Active Disruptions
Disruption ID | Type | Severity | Location | Started | Est. Resolution | Affected Routes | Delayed Deliveries | Additional Cost
DISR-00001 | STRIKE | CRITICAL | Mexican Border | 8/2/2025, 10:00:35 AM | 8/2/2025, 5:00:35 PM | 3 | 33 | $5,666.022
DISR-00003 | WEATHER | MEDIUM | Port of LA | 8/1/2025, 5:00:35 PM | 8/2/2025, 10:00:35 AM | 4 | 40 | $4,338.934
DISR-00006 | WEATHER | CRITICAL | Highway 101 | 8/1/2025, 1:00:35 PM | 8/2/2025, 11:00:35 AM | 7 | 98 | $14,002.733
DISR-00010 | EQUIPMENT | MEDIUM | Mexican Border | 8/1/2025, 12:00:35 PM | 8/2/2025, 8:00:35 AM | 8 | 96 | $11,604.581

## Impact Analysis
Metric | Value
Total Disruptions | 10
Active Disruptions | 4
Total Delayed Deliveries | 561
Total Additional Cost | $80,468.586
Affected Customers | 448
Average Resolution Time | 4.5 hours

## Mitigation Actions
Disruption ID | Action | Priority | Status | Responsible
DISR-00001 | Reroute affected vehicles | IMMEDIATE | Planned | Operations Team
DISR-00001 | Notify customers of delays | IMMEDIATE | Planned | Operations Team
DISR-00003 | Reroute affected vehicles | MEDIUM | Planned | Operations Team
DISR-00003 | Notify customers of delays | MEDIUM | In Progress | Operations Team
DISR-00003 | Deploy backup resources | MEDIUM | In Progress | Operations Team
DISR-00006 | Reroute affected vehicles | IMMEDIATE | Planned | Operations Team
DISR-00006 | Notify customers of delays | IMMEDIATE | In Progress | Operations Team
DISR-00006 | Deploy backup resources | IMMEDIATE | Planned | Operations Team
DISR-00010 | Reroute affected vehicles | MEDIUM | In Progress | Operations Team
DISR-00010 | Notify customers of delays | MEDIUM | Planned | Operations Team

## Historical Analysis
Month | Disruptions | Avg Resolution (hrs) | Total Cost
January | 12 | 4.2 | $45,000
February | 8 | 3.8 | $32,000
March | 15 | 5.1 | $58,000
April | 10 | 3.5 | $38,000