## Report Information
Property | Value
Report Name | Supply Chain Disruption Report
Description | Real-time disruption monitoring and mitigation
Generated By | Vanguard Disruption Manager
Use Case | supply-chain-disruption
Workflow ID | disruption-report
Generated At | 2025-08-03T13:02:35.982Z

## Active Disruptions
Disruption ID | Type | Severity | Location | Started | Est. Resolution | Affected Routes | Delayed Deliveries | Additional Cost
DISR-00003 | CUSTOMS | MEDIUM | Chicago Hub | 8/1/2025, 12:02:35 PM | 8/2/2025, 3:02:35 AM | 6 | 84 | $4,729.65
DISR-00007 | CUSTOMS | HIGH | Port of LA | 8/2/2025, 7:02:35 PM | 8/2/2025, 10:02:35 PM | 7 | 42 | $5,173.226
DISR-00008 | WEATHER | HIGH | Port of LA | 8/2/2025, 9:02:35 PM | 8/3/2025, 1:02:35 PM | 6 | 30 | $3,404.125
DISR-00009 | STRIKE | CRITICAL | Chicago Hub | 8/3/2025, 4:02:35 AM | 8/3/2025, 8:02:35 AM | 10 | 110 | $8,430.365

## Impact Analysis
Metric | Value
Total Disruptions | 10
Active Disruptions | 4
Total Delayed Deliveries | 610
Total Additional Cost | $63,104.255
Affected Customers | 488
Average Resolution Time | 4.5 hours

## Mitigation Actions
Disruption ID | Action | Priority | Status | Responsible
DISR-00003 | Reroute affected vehicles | MEDIUM | In Progress | Operations Team
DISR-00003 | Notify customers of delays | MEDIUM | Planned | Operations Team
DISR-00003 | Deploy backup resources | MEDIUM | Planned | Operations Team
DISR-00007 | Reroute affected vehicles | HIGH | Planned | Operations Team
DISR-00007 | Notify customers of delays | HIGH | In Progress | Operations Team
DISR-00008 | Reroute affected vehicles | HIGH | In Progress | Operations Team
DISR-00008 | Notify customers of delays | HIGH | In Progress | Operations Team
DISR-00008 | Deploy backup resources | HIGH | Planned | Operations Team
DISR-00009 | Reroute affected vehicles | IMMEDIATE | Planned | Operations Team
DISR-00009 | Notify customers of delays | IMMEDIATE | Planned | Operations Team
DISR-00009 | Deploy backup resources | IMMEDIATE | Planned | Operations Team

## Historical Analysis
Month | Disruptions | Avg Resolution (hrs) | Total Cost
January | 12 | 4.2 | $45,000
February | 8 | 3.8 | $32,000
March | 15 | 5.1 | $58,000
April | 10 | 3.5 | $38,000