## Report Information
Property | Value
Report Name | Supply Chain Disruption Report
Description | Real-time disruption monitoring and mitigation
Generated By | Vanguard Disruption Manager
Use Case | supply-chain-disruption
Workflow ID | disruption-report
Generated At | 2025-08-03T13:05:49.780Z

## Active Disruptions
Disruption ID | Type | Severity | Location | Started | Est. Resolution | Affected Routes | Delayed Deliveries | Additional Cost
DISR-00001 | TRAFFIC | LOW | Highway 101 | 8/1/2025, 9:05:49 AM | 8/1/2025, 11:05:49 PM | 6 | 72 | $7,365.889
DISR-00002 | TRAFFIC | CRITICAL | Port of LA | 8/1/2025, 1:05:49 PM | 8/2/2025, 5:05:49 AM | 10 | 110 | $6,780.007
DISR-00003 | WEATHER | MEDIUM | JFK Airport | 8/3/2025, 5:05:49 AM | 8/4/2025, 6:05:49 AM | 6 | 60 | $6,519.92
DISR-00004 | CUSTOMS | HIGH | Port of LA | 8/3/2025, 2:05:49 AM | 8/3/2025, 12:05:49 PM | 5 | 30 | $5,322.441
DISR-00007 | CUSTOMS | MEDIUM | JFK Airport | 8/2/2025, 10:05:49 AM | 8/2/2025, 12:05:49 PM | 2 | 28 | $3,702.994
DISR-00008 | CUSTOMS | HIGH | Port of LA | 8/1/2025, 11:05:49 PM | 8/2/2025, 2:05:49 AM | 2 | 20 | $1,787.455

## Impact Analysis
Metric | Value
Total Disruptions | 10
Active Disruptions | 6
Total Delayed Deliveries | 506
Total Additional Cost | $61,697.651
Affected Customers | 404
Average Resolution Time | 4.5 hours

## Mitigation Actions
Disruption ID | Action | Priority | Status | Responsible
DISR-00001 | Reroute affected vehicles | MEDIUM | Planned | Operations Team
DISR-00001 | Notify customers of delays | MEDIUM | In Progress | Operations Team
DISR-00002 | Reroute affected vehicles | IMMEDIATE | Planned | Operations Team
DISR-00002 | Notify customers of delays | IMMEDIATE | Planned | Operations Team
DISR-00002 | Deploy backup resources | IMMEDIATE | In Progress | Operations Team
DISR-00003 | Reroute affected vehicles | MEDIUM | Planned | Operations Team
DISR-00003 | Notify customers of delays | MEDIUM | Planned | Operations Team
DISR-00004 | Reroute affected vehicles | HIGH | In Progress | Operations Team
DISR-00004 | Notify customers of delays | HIGH | In Progress | Operations Team
DISR-00004 | Deploy backup resources | HIGH | In Progress | Operations Team
DISR-00007 | Reroute affected vehicles | MEDIUM | In Progress | Operations Team
DISR-00007 | Notify customers of delays | MEDIUM | Planned | Operations Team
DISR-00007 | Deploy backup resources | MEDIUM | Planned | Operations Team
DISR-00008 | Reroute affected vehicles | HIGH | Planned | Operations Team
DISR-00008 | Notify customers of delays | HIGH | Planned | Operations Team
DISR-00008 | Deploy backup resources | HIGH | In Progress | Operations Team

## Historical Analysis
Month | Disruptions | Avg Resolution (hrs) | Total Cost
January | 12 | 4.2 | $45,000
February | 8 | 3.8 | $32,000
March | 15 | 5.1 | $58,000
April | 10 | 3.5 | $38,000