## Report Information
Property | Value
Report Name | Supply Chain Disruption Report
Description | Real-time disruption monitoring and mitigation
Generated By | Vanguard Disruption Manager
Use Case | supply-chain-disruption
Workflow ID | disruption-report
Generated At | 2025-08-03T13:03:26.847Z

## Active Disruptions
Disruption ID | Type | Severity | Location | Started | Est. Resolution | Affected Routes | Delayed Deliveries | Additional Cost
DISR-00001 | WEATHER | LOW | Chicago Hub | 8/2/2025, 3:03:26 PM | 8/3/2025, 2:03:26 AM | 6 | 36 | $6,926.465
DISR-00005 | ACCIDENT | LOW | JFK Airport | 8/2/2025, 1:03:26 AM | 8/2/2025, 3:03:26 AM | 9 | 126 | $14,384.25
DISR-00006 | STRIKE | MEDIUM | Highway 101 | 8/2/2025, 12:03:26 AM | 8/3/2025, 12:03:26 AM | 5 | 50 | $7,466.71
DISR-00007 | TRAFFIC | LOW | Highway 101 | 8/2/2025, 5:03:26 PM | 8/3/2025, 10:03:26 AM | 8 | 48 | $3,150.829
DISR-00008 | CUSTOMS | LOW | Mexican Border | 8/2/2025, 1:03:26 AM | 8/2/2025, 3:03:26 AM | 2 | 20 | $3,999.569

## Impact Analysis
Metric | Value
Total Disruptions | 10
Active Disruptions | 5
Total Delayed Deliveries | 699
Total Additional Cost | $83,657.952
Affected Customers | 559
Average Resolution Time | 4.5 hours

## Mitigation Actions
Disruption ID | Action | Priority | Status | Responsible
DISR-00001 | Reroute affected vehicles | MEDIUM | Planned | Operations Team
DISR-00001 | Notify customers of delays | MEDIUM | In Progress | Operations Team
DISR-00005 | Reroute affected vehicles | MEDIUM | Planned | Operations Team
DISR-00005 | Notify customers of delays | MEDIUM | Planned | Operations Team
DISR-00006 | Reroute affected vehicles | MEDIUM | In Progress | Operations Team
DISR-00006 | Notify customers of delays | MEDIUM | In Progress | Operations Team
DISR-00006 | Deploy backup resources | MEDIUM | Planned | Operations Team
DISR-00007 | Reroute affected vehicles | MEDIUM | Planned | Operations Team
DISR-00007 | Notify customers of delays | MEDIUM | Planned | Operations Team
DISR-00008 | Reroute affected vehicles | MEDIUM | Planned | Operations Team
DISR-00008 | Notify customers of delays | MEDIUM | Planned | Operations Team
DISR-00008 | Deploy backup resources | MEDIUM | Planned | Operations Team

## Historical Analysis
Month | Disruptions | Avg Resolution (hrs) | Total Cost
January | 12 | 4.2 | $45,000
February | 8 | 3.8 | $32,000
March | 15 | 5.1 | $58,000
April | 10 | 3.5 | $38,000