## Report Information
Property | Value
Report Name | Supply Chain Disruption Report
Description | Real-time disruption monitoring and mitigation
Generated By | Vanguard Disruption Manager
Use Case | supply-chain-disruption
Workflow ID | disruption-report
Generated At | 2025-08-03T13:08:06.786Z

## Active Disruptions
Disruption ID | Type | Severity | Location | Started | Est. Resolution | Affected Routes | Delayed Deliveries | Additional Cost
DISR-00001 | EQUIPMENT | MEDIUM | JFK Airport | 8/2/2025, 5:08:06 PM | 8/3/2025, 4:08:06 AM | 9 | 117 | $7,967.168
DISR-00006 | EQUIPMENT | CRITICAL | JFK Airport | 8/2/2025, 9:08:06 PM | 8/3/2025, 7:08:06 PM | 7 | 91 | $11,807.796
DISR-00008 | TRAFFIC | CRITICAL | Highway 101 | 8/2/2025, 12:08:06 PM | 8/3/2025, 1:08:06 PM | 2 | 18 | $910.447

## Impact Analysis
Metric | Value
Total Disruptions | 10
Active Disruptions | 3
Total Delayed Deliveries | 553
Total Additional Cost | $65,670.614
Affected Customers | 442
Average Resolution Time | 4.5 hours

## Mitigation Actions
Disruption ID | Action | Priority | Status | Responsible
DISR-00001 | Reroute affected vehicles | MEDIUM | In Progress | Operations Team
DISR-00001 | Notify customers of delays | MEDIUM | Planned | Operations Team
DISR-00001 | Deploy backup resources | MEDIUM | In Progress | Operations Team
DISR-00006 | Reroute affected vehicles | IMMEDIATE | Planned | Operations Team
DISR-00006 | Notify customers of delays | IMMEDIATE | Planned | Operations Team
DISR-00006 | Deploy backup resources | IMMEDIATE | In Progress | Operations Team
DISR-00008 | Reroute affected vehicles | IMMEDIATE | Planned | Operations Team
DISR-00008 | Notify customers of delays | IMMEDIATE | Planned | Operations Team
DISR-00008 | Deploy backup resources | IMMEDIATE | Planned | Operations Team

## Historical Analysis
Month | Disruptions | Avg Resolution (hrs) | Total Cost
January | 12 | 4.2 | $45,000
February | 8 | 3.8 | $32,000
March | 15 | 5.1 | $58,000
April | 10 | 3.5 | $38,000