## Report Information
Property | Value
Report Name | Supply Chain Disruption Report
Description | Real-time disruption monitoring and mitigation
Generated By | Vanguard Disruption Manager
Use Case | supply-chain-disruption
Workflow ID | disruption-report
Generated At | 2025-08-03T13:08:27.317Z

## Active Disruptions
Disruption ID | Type | Severity | Location | Started | Est. Resolution | Affected Routes | Delayed Deliveries | Additional Cost
DISR-00003 | EQUIPMENT | HIGH | JFK Airport | 8/2/2025, 5:08:27 PM | 8/3/2025, 12:08:27 AM | 8 | 104 | $7,317.237
DISR-00005 | TRAFFIC | LOW | Highway 101 | 8/3/2025, 2:08:27 AM | 8/3/2025, 10:08:27 AM | 5 | 70 | $13,426.056
DISR-00007 | TRAFFIC | HIGH | Chicago Hub | 8/1/2025, 3:08:27 PM | 8/1/2025, 7:08:27 PM | 7 | 49 | $6,055.735
DISR-00010 | STRIKE | HIGH | Highway 101 | 8/1/2025, 11:08:27 PM | 8/2/2025, 10:08:27 PM | 3 | 21 | $1,552.507

## Impact Analysis
Metric | Value
Total Disruptions | 10
Active Disruptions | 4
Total Delayed Deliveries | 654
Total Additional Cost | $95,743.819
Affected Customers | 523
Average Resolution Time | 4.5 hours

## Mitigation Actions
Disruption ID | Action | Priority | Status | Responsible
DISR-00003 | Reroute affected vehicles | HIGH | Planned | Operations Team
DISR-00003 | Notify customers of delays | HIGH | In Progress | Operations Team
DISR-00003 | Deploy backup resources | HIGH | In Progress | Operations Team
DISR-00005 | Reroute affected vehicles | MEDIUM | Planned | Operations Team
DISR-00005 | Notify customers of delays | MEDIUM | Planned | Operations Team
DISR-00007 | Reroute affected vehicles | HIGH | Planned | Operations Team
DISR-00007 | Notify customers of delays | HIGH | In Progress | Operations Team
DISR-00010 | Reroute affected vehicles | HIGH | Planned | Operations Team
DISR-00010 | Notify customers of delays | HIGH | Planned | Operations Team
DISR-00010 | Deploy backup resources | HIGH | Planned | Operations Team

## Historical Analysis
Month | Disruptions | Avg Resolution (hrs) | Total Cost
January | 12 | 4.2 | $45,000
February | 8 | 3.8 | $32,000
March | 15 | 5.1 | $58,000
April | 10 | 3.5 | $38,000