## Report Information
Property | Value
Report Name | Supply Chain Disruption Report
Description | Real-time disruption monitoring and mitigation
Generated By | Vanguard Disruption Manager
Use Case | supply-chain-disruption
Workflow ID | disruption-report
Generated At | 2025-08-03T13:07:48.825Z

## Active Disruptions
Disruption ID | Type | Severity | Location | Started | Est. Resolution | Affected Routes | Delayed Deliveries | Additional Cost
DISR-00005 | STRIKE | HIGH | Highway 101 | 8/3/2025, 4:07:48 AM | 8/4/2025, 5:07:48 AM | 3 | 39 | $2,289.988
DISR-00008 | CUSTOMS | HIGH | Chicago Hub | 8/2/2025, 8:07:48 AM | 8/2/2025, 10:07:48 AM | 7 | 91 | $9,620.293

## Impact Analysis
Metric | Value
Total Disruptions | 10
Active Disruptions | 2
Total Delayed Deliveries | 657
Total Additional Cost | $77,883.021
Affected Customers | 525
Average Resolution Time | 4.5 hours

## Mitigation Actions
Disruption ID | Action | Priority | Status | Responsible
DISR-00005 | Reroute affected vehicles | HIGH | In Progress | Operations Team
DISR-00005 | Notify customers of delays | HIGH | In Progress | Operations Team
DISR-00005 | Deploy backup resources | HIGH | Planned | Operations Team
DISR-00008 | Reroute affected vehicles | HIGH | Planned | Operations Team
DISR-00008 | Notify customers of delays | HIGH | In Progress | Operations Team

## Historical Analysis
Month | Disruptions | Avg Resolution (hrs) | Total Cost
January | 12 | 4.2 | $45,000
February | 8 | 3.8 | $32,000
March | 15 | 5.1 | $58,000
April | 10 | 3.5 | $38,000