## Report Information
Property | Value
Report Name | Supply Chain Disruption Report
Description | Real-time disruption monitoring and mitigation
Generated By | Vanguard Disruption Manager
Use Case | supply-chain-disruption
Workflow ID | disruption-report
Generated At | 2025-08-03T13:00:45.660Z

## Active Disruptions
Disruption ID | Type | Severity | Location | Started | Est. Resolution | Affected Routes | Delayed Deliveries | Additional Cost
DISR-00001 | STRIKE | HIGH | Mexican Border | 8/1/2025, 10:00:45 PM | 8/2/2025, 2:00:45 PM | 6 | 30 | $5,943.707
DISR-00002 | EQUIPMENT | LOW | Chicago Hub | 8/1/2025, 10:00:45 PM | 8/2/2025, 4:00:45 AM | 5 | 25 | $2,029.597
DISR-00006 | CUSTOMS | HIGH | Mexican Border | 8/3/2025, 7:00:45 AM | 8/3/2025, 9:00:45 PM | 9 | 117 | $8,595.288
DISR-00007 | ACCIDENT | MEDIUM | Chicago Hub | 8/2/2025, 9:00:45 PM | 8/3/2025, 12:00:45 PM | 8 | 96 | $17,805.64

## Impact Analysis
Metric | Value
Total Disruptions | 10
Active Disruptions | 4
Total Delayed Deliveries | 681
Total Additional Cost | $80,531.287
Affected Customers | 544
Average Resolution Time | 4.5 hours

## Mitigation Actions
Disruption ID | Action | Priority | Status | Responsible
DISR-00001 | Reroute affected vehicles | HIGH | Planned | Operations Team
DISR-00001 | Notify customers of delays | HIGH | Planned | Operations Team
DISR-00001 | Deploy backup resources | HIGH | Planned | Operations Team
DISR-00002 | Reroute affected vehicles | MEDIUM | In Progress | Operations Team
DISR-00002 | Notify customers of delays | MEDIUM | In Progress | Operations Team
DISR-00002 | Deploy backup resources | MEDIUM | In Progress | Operations Team
DISR-00006 | Reroute affected vehicles | HIGH | In Progress | Operations Team
DISR-00006 | Notify customers of delays | HIGH | Planned | Operations Team
DISR-00007 | Reroute affected vehicles | MEDIUM | In Progress | Operations Team
DISR-00007 | Notify customers of delays | MEDIUM | In Progress | Operations Team
DISR-00007 | Deploy backup resources | MEDIUM | In Progress | Operations Team

## Historical Analysis
Month | Disruptions | Avg Resolution (hrs) | Total Cost
January | 12 | 4.2 | $45,000
February | 8 | 3.8 | $32,000
March | 15 | 5.1 | $58,000
April | 10 | 3.5 | $38,000