## Report Information
Property | Value
Report Name | Supply Chain Disruption Report
Description | Real-time disruption monitoring and mitigation
Generated By | Vanguard Disruption Manager
Use Case | supply-chain-disruption
Workflow ID | disruption-report
Generated At | 2025-08-03T13:02:08.877Z

## Active Disruptions
Disruption ID | Type | Severity | Location | Started | Est. Resolution | Affected Routes | Delayed Deliveries | Additional Cost
DISR-00001 | STRIKE | LOW | Port of LA | 8/2/2025, 7:02:08 AM | 8/3/2025, 8:02:08 AM | 1 | 12 | $1,046.795
DISR-00007 | STRIKE | LOW | Chicago Hub | 8/2/2025, 11:02:08 AM | 8/3/2025, 1:02:08 AM | 5 | 50 | $3,040.313
DISR-00008 | WEATHER | MEDIUM | JFK Airport | 8/2/2025, 5:02:08 PM | 8/3/2025, 5:02:08 AM | 10 | 130 | $10,311.703
DISR-00009 | ACCIDENT | LOW | Mexican Border | 8/2/2025, 12:02:08 AM | 8/2/2025, 6:02:08 PM | 1 | 10 | $1,076.072

## Impact Analysis
Metric | Value
Total Disruptions | 10
Active Disruptions | 4
Total Delayed Deliveries | 489
Total Additional Cost | $43,624.319
Affected Customers | 391
Average Resolution Time | 4.5 hours

## Mitigation Actions
Disruption ID | Action | Priority | Status | Responsible
DISR-00001 | Reroute affected vehicles | MEDIUM | In Progress | Operations Team
DISR-00001 | Notify customers of delays | MEDIUM | Planned | Operations Team
DISR-00007 | Reroute affected vehicles | MEDIUM | Planned | Operations Team
DISR-00007 | Notify customers of delays | MEDIUM | Planned | Operations Team
DISR-00007 | Deploy backup resources | MEDIUM | Planned | Operations Team
DISR-00008 | Reroute affected vehicles | MEDIUM | In Progress | Operations Team
DISR-00008 | Notify customers of delays | MEDIUM | Planned | Operations Team
DISR-00008 | Deploy backup resources | MEDIUM | In Progress | Operations Team
DISR-00009 | Reroute affected vehicles | MEDIUM | In Progress | Operations Team
DISR-00009 | Notify customers of delays | MEDIUM | In Progress | Operations Team

## Historical Analysis
Month | Disruptions | Avg Resolution (hrs) | Total Cost
January | 12 | 4.2 | $45,000
February | 8 | 3.8 | $32,000
March | 15 | 5.1 | $58,000
April | 10 | 3.5 | $38,000