## Report Information
Property | Value
Report Name | Supply Chain Disruption Report
Description | Real-time disruption monitoring and mitigation
Generated By | Vanguard Disruption Manager
Use Case | supply-chain-disruption
Workflow ID | disruption-report
Generated At | 2025-08-03T13:04:50.748Z

## Active Disruptions
Disruption ID | Type | Severity | Location | Started | Est. Resolution | Affected Routes | Delayed Deliveries | Additional Cost
DISR-00003 | CUSTOMS | HIGH | JFK Airport | 8/2/2025, 8:04:50 AM | 8/2/2025, 9:04:50 PM | 8 | 56 | $9,779.013
DISR-00004 | STRIKE | HIGH | Mexican Border | 8/2/2025, 11:04:50 PM | 8/3/2025, 2:04:50 AM | 5 | 45 | $6,743.083
DISR-00008 | ACCIDENT | CRITICAL | Mexican Border | 8/3/2025, 4:04:50 AM | 8/3/2025, 6:04:50 AM | 3 | 15 | $1,873.429

## Impact Analysis
Metric | Value
Total Disruptions | 10
Active Disruptions | 3
Total Delayed Deliveries | 565
Total Additional Cost | $76,156.327
Affected Customers | 452
Average Resolution Time | 4.5 hours

## Mitigation Actions
Disruption ID | Action | Priority | Status | Responsible
DISR-00003 | Reroute affected vehicles | HIGH | In Progress | Operations Team
DISR-00003 | Notify customers of delays | HIGH | Planned | Operations Team
DISR-00004 | Reroute affected vehicles | HIGH | In Progress | Operations Team
DISR-00004 | Notify customers of delays | HIGH | In Progress | Operations Team
DISR-00004 | Deploy backup resources | HIGH | In Progress | Operations Team
DISR-00008 | Reroute affected vehicles | IMMEDIATE | Planned | Operations Team
DISR-00008 | Notify customers of delays | IMMEDIATE | Planned | Operations Team

## Historical Analysis
Month | Disruptions | Avg Resolution (hrs) | Total Cost
January | 12 | 4.2 | $45,000
February | 8 | 3.8 | $32,000
March | 15 | 5.1 | $58,000
April | 10 | 3.5 | $38,000