## Report Information
Property | Value
Report Name | Supply Chain Disruption Report
Description | Real-time disruption monitoring and mitigation
Generated By | Vanguard Disruption Manager
Use Case | supply-chain-disruption
Workflow ID | disruption-report
Generated At | 2025-08-03T13:03:09.676Z

## Active Disruptions
Disruption ID | Type | Severity | Location | Started | Est. Resolution | Affected Routes | Delayed Deliveries | Additional Cost
DISR-00002 | CUSTOMS | MEDIUM | Chicago Hub | 8/2/2025, 5:03:09 PM | 8/3/2025, 7:03:09 AM | 8 | 72 | $4,582.494
DISR-00004 | CUSTOMS | HIGH | Highway 101 | 8/2/2025, 12:03:09 PM | 8/2/2025, 11:03:09 PM | 7 | 91 | $11,405.017
DISR-00010 | WEATHER | LOW | Mexican Border | 8/1/2025, 6:03:09 PM | 8/2/2025, 5:03:09 PM | 9 | 63 | $4,980.085

## Impact Analysis
Metric | Value
Total Disruptions | 10
Active Disruptions | 3
Total Delayed Deliveries | 566
Total Additional Cost | $68,677.311
Affected Customers | 452
Average Resolution Time | 4.5 hours

## Mitigation Actions
Disruption ID | Action | Priority | Status | Responsible
DISR-00002 | Reroute affected vehicles | MEDIUM | In Progress | Operations Team
DISR-00002 | Notify customers of delays | MEDIUM | Planned | Operations Team
DISR-00004 | Reroute affected vehicles | HIGH | Planned | Operations Team
DISR-00004 | Notify customers of delays | HIGH | In Progress | Operations Team
DISR-00004 | Deploy backup resources | HIGH | In Progress | Operations Team
DISR-00010 | Reroute affected vehicles | MEDIUM | Planned | Operations Team
DISR-00010 | Notify customers of delays | MEDIUM | Planned | Operations Team

## Historical Analysis
Month | Disruptions | Avg Resolution (hrs) | Total Cost
January | 12 | 4.2 | $45,000
February | 8 | 3.8 | $32,000
March | 15 | 5.1 | $58,000
April | 10 | 3.5 | $38,000